## Summary
Bunko black-box usability rounds (T-105). Target: every score at least 8/10.
Area | Round 1 | Round 2 | Round 3 | Round 4 | Round 5
First impression onboarding | 6 | 8 | 7 | 7 | 8
Library adding finding books | 5 | 7 | 5 | 6 | 7
Book page and details | 5 | 6 | 5 | 6 | 8
Reading experience | 2 | 5 | not tested | 5 | 9
Tracking journal statistics | 4 | 6 | 7 | 8 | 6
Shelves organizing | 6 | 7 | 6 | 8 | 6
Notes highlights reviews | 6 | 5 | 5 | 5 | 7
Assistant chat | 4 | 6 | 6 | 7 | 7
Look and feel | 7 | 8 | 7 | 8 | 9
Speed reliability | 4 | 5 | 6 | 6 | 6
Overall | 4 | 6 | 6 | 6 | 7
Lowest score | 2 | 5 | 5 | 5 | 6
Issues reported | 17 | 28 | 15 | 17 | 9
Issues fixed | 14 | 22 | 11 | 10 | 0
Round 1 (2026-10-23) | Local: frontend :5174, API :3100 with AI_PROVIDER=nvidia but no NVIDIA_API_KEY yet; Claude ai-service not running. Seeded account with 6 books (one sample EPUB).
Round 2 (2026-10-23) | Local: frontend :5174, API :3100; assistant model not configured (no NVIDIA_API_KEY), tester told so. Fresh seeded account with an original 5-chapter EPUB.
Round 3 (2026-10-23) | Local: frontend :5174, API :3100; assistant model not configured (no NVIDIA_API_KEY). The seeded account's password reached the tester in a follow-up message, which its safety check refused to type, so it tested with a fresh account that had no EPUB: the reader was not tested this round.
Round 4 (2026-10-23) | Local: frontend :5174, API :3100; assistant model not configured (no NVIDIA_API_KEY). Browser pane already signed in to the seeded account with the readable EPUB; desktop (800px pane) and phone 375x812.
Round 5 (2026-10-28) | Local: frontend :5174, API :3100 with AI_PROVIDER=nvidia and a real NVIDIA_API_KEY (live model calls, no mock). Seeded fresh account (qa.round5.1793127205@bunko.test) with AI consent pre-granted, a small library, two shelves, and one readable EPUB.

## All issues
Round | ID | Area | Severity | Title | Steps | Expected | Actual | Root cause | Fix | Files | Commit | Status | Verified in round
1 | R1-01 | Reading experience | blocker | No way to open the digital reader, even for a book with an EPUB | Library > 'A Bunko Sample Book' > 'Open Digital Reader'; clicked the EPUB edition row; tried status Reading, reload, and 'Start / Resume Reading Session'. | The EPUB opens in the reader. | Every path lands on the book details page; the EPUB edition row has no read button. | QA seed attached the EPUB with the upload id instead of the stored file id, so no copy existed; and the app gave a digital edition without its file no way forward. | Seed fixed (uses the id /files/:id/confirm returns) and now ships an original 5-chapter novella. A digital edition with no file shows 'Upload file'; the quick-action modal only offers actions that work. | backend/scripts/seed-qa-reader.ts, backend/scripts/qa-sample-book.ts, frontend/src/features/library/BookDetailPage.tsx, frontend/src/features/library/AddEditionDialog.tsx, frontend/src/features/library/BookQuickActionModal.tsx |  | Fixed
1 | R1-02 | Library adding finding books | major | Most covers are for completely different books | Open Library (also Shelves, modal, book page). | The real cover for each book. | The Left Hand of Darkness and the sample book show 'Their Eyes Were Watching God'; Circe, Piranesi and Klara show unrelated books; a hand-added zine got a random cover. There's no way to change or remove a cover. | Three code paths took the first search result with any cover regardless of title; the seed also used guessed cover ids. Wikidata series discovery filed books under their own title. | Covers only from a result with the same main title and a shared author surname (pickMatchingCover), looked up in the background; self-named series ignored and cleared. Changing/removing a cover by hand is not built yet (covers live on the shared catalogue entry). | backend/src/modules/library/library.service.ts, backend/scripts/seed-qa-reader.ts |  | Partly fixed
1 | R1-03 | Assistant chat | major | Many assistant messages fail with a generic error | 'no i meant the zevin one...', 'I started Tomorrow, and Tomorrow, and Tomorrow' (the app's own example), 'ok i started the first one. and dnf'd circe tbh', 'and add it to my comfort reads shelf', 'rate it 5 stars actually'. | The change is made, or a clarifying question. | 'An unexpected error occurred' each time, no reason, no retry. Short single-book commands worked. | No NVIDIA key on the test server: NIM's 401 became a plain Error and surfaced as a 500. Separately, titles with commas, filler words ('ok', 'and', 'tbh', 'actually') and 'it' defeated the fast paths, so those messages needed the model. | Rejected key / rate limit are 'unavailable'; a missing key is detected at startup and answered with a plain message; any other failure is a friendly logged reply. Owned titles with commas are masked before clause splitting; filler words stripped. | backend/src/modules/assistant/clients/NvidiaNimClient.ts, backend/src/modules/assistant/aiController.ts, backend/src/modules/assistant/domains/books/conversation/quickCommands.ts |  | Fixed
1 | R1-04 | Assistant chat | major | A typo in an owned title makes it search the catalogue for junk | 'started tomorow and tomorrow last night, its so good already' (the book is in the library). | It matches the owned book. | "I couldn't find a book called \"tomorow\". The closest were \"Notes on the History of Fort George\"..." | Title matching needed exact words; the list splitter split 'tomorow and tomorrow' into two books. | Typo-tolerant word matching on owned titles; lists split only into books the reader owns. | backend/src/modules/assistant/domains/books/text/match.ts, backend/src/modules/assistant/domains/books/conversation/quickCommands.ts |  | Fixed
1 | R1-05 | Assistant chat | major | Recommendations made up a sequel and ignored 'something like Piranesi' | 'what should i read next? something like piranesi' | Books like Piranesi, and accurate facts. | Listed the Want to Read list only, and said 'the series continues with Dune II by Frank Herbert' (no such book). | The 'series continues' line came from a Wikidata lookup that returned non-books ('Dune II'); 'like X' wasn't used. | Series continuation removed; 'something like X' ranks the list by X's authors and genres with reasons, and asks the model for books beyond the list. | backend/src/modules/assistant/domains/books/actions/readTools.ts, backend/src/modules/assistant/domains/books/pipeline/preRoute.ts, backend/src/modules/assistant/domains/books/prompts/answerPrompt.ts |  | Fixed
1 | R1-06 | Tracking journal statistics | major | Journal entries don't say which book | Piranesi > physical edition > session > end with 'p 112' and a reflection > Journal. | Entry shows the book, page and time, and links to it. | 'Oct 23, 2026 · 0 min · “the other is kinda sus now”': no title, no page, not clickable; no way to add an entry from the Journal. | Journal entries carried no book. | Each entry names and links its book with its cover and format; 'Log reading' on the Journal. | backend/src/modules/journal/journal.service.ts, frontend/src/features/journal/JournalPage.tsx |  | Fixed
1 | R1-07 | Tracking journal statistics | major | Reading can only be logged live, and pages aren't counted | Started and immediately ended a session with 'p 112'. | Log a past session (time, date, page), and pages count. | 'Session saved — 0 min. Nice reading.' Stats: 'Pages read 0'. No manual duration/date, no progress on the book, no finish date. | Only live timed sessions existed; a physical session with only an end page can't count pages. | POST /reading-sessions/log and a 'Log reading' form (book, day, minutes, from/to page, reflection) on the Journal and book page; both pages make them count. | backend/src/modules/reading-sessions/*, frontend/src/features/journal/LogSessionDialog.tsx |  | Fixed
1 | R1-08 | Book page and details | major | Modal buttons silently do nothing without a matching edition | Circe (no editions) > 'Start / Resume Reading Session'; Piranesi (physical only) > 'Open Digital Reader'. | Hidden, disabled, or explained. | Both silently go to the book page. | Modal buttons fell back to navigating to the book page. | Modal shows only working actions and explains/offers to add a copy otherwise. | frontend/src/features/library/BookQuickActionModal.tsx |  | Fixed
1 | R1-09 | Tracking journal statistics | minor | Statistics contradict themselves; language data messy | Statistics > Daily. | Consistent numbers. | Summary counts 1 session while the chart says 'No reading sessions in this period yet'; languages 'Unknown 6' and lowercase 'english 2'; 'Bunko' listed as an author. | The chart's empty state keyed on minutes, not sessions; language labels weren't normalised. | Chart distinguishes 'no sessions' from 'sessions under a minute'; languages shown as names. ('Bunko' as author was seed data; reading goals aren't in the SRS.) | frontend/src/features/statistics/ActivityChart.tsx, backend/src/modules/statistics/statistics.service.ts |  | Fixed
1 | R1-10 | Library adding finding books | minor | Catalogue search isn't typo-tolerant and is slow; no status on add | Add a book > 'tomorow and tomorrow and tomorrow'. | The right book near the top. | After 6-8s: unrelated results. Confusing language chips; manual form lacks page count/cover; always added as Want to Read. | Google Books answered first with poor relevance; the universe check could hijack results; no caching; original language defaulted to 'Japanese'. | Open Library title search merged in; results ranked by title match; universe check only for named universes; searches cached an hour; choose Want to read / Reading now / Already read when adding; calm metadata line replaces off-palette chips. (Catalogue-side typo tolerance depends on the providers.) | backend/src/modules/metadata/metadata.service.ts, frontend/src/features/library/AddBookDialog.tsx |  | Fixed
1 | R1-11 | Library adding finding books | minor | 'Remove from library' gave no visible response | Book page > 'Remove from library'. | A confirmation, then the book is gone. | Nothing visible; the book stayed. | Used the browser's native confirm(), which the tester never saw. | In-app confirmation dialog that says what's kept. | frontend/src/features/library/BookDetailPage.tsx |  | Fixed
1 | R1-12 | Shelves organizing | minor | Odd shelf grouping, per-row scrollbars, inverted toggle | Shelves > All Volumes; Covers/Spines toggle; mobile. | Books share shelves; the active view is clear. | One book per tall row under its own title; every row has a scrollbar; the active toggle option is the dim one; the choice doesn't stick; arrows cover art on mobile. | Rows per one-book series/genre; overflow-x-auto made rows scroll vertically; active toggle was the dark pill; arrows forced visible on mobile. | Rows need two books; overflow-y hidden with a thin themed scrollbar; light active pill with aria-pressed, remembered; arrows on focus/hover only. | frontend/src/features/shelves/* |  | Fixed
1 | R1-13 | Speed reliability | minor | Slow loads with little feedback | Library, Shelves, book pages; status dropdown. | Fast, with placeholders. | Covers blank for 3-5s on every visit; a big modal spinner; status change ~3s while the old value still shows. | Opening a book ran series discovery and a cover search synchronously (2-3s); covers had no placeholder; status change waited for the server. | Both moved to the background (book fetch ~72 ms); lazy covers on a paper tint; skeleton in the modal; optimistic status updates. | backend/src/modules/library/library.service.ts, frontend/src/features/library/BookCover.tsx, frontend/src/lib/api/works.ts |  | Fixed
1 | R1-14 | Notes highlights reviews | minor | Reviews and notes are basic | Rated, reviewed, added and edited a note. | Half stars, dated notes, spoiler/private options. | Whole stars only; notes undated with only a 'Book' tag; highlights impossible (R1-01). | Notes showed no date; ratings are whole stars by SRS §14. | Notes show their date (and position); the review box says reviews and notes are private. Half stars not added: SRS §14 sets whole 5-star ratings. | frontend/src/features/notes/NotesPanel.tsx, frontend/src/features/reviews/ReviewPanel.tsx |  | Partly fixed
1 | R1-15 | Assistant chat | polish | Odd reply after declining a follow-up | 'rate piranesi 5 stars' > asked to mark Finished > 'nah not yet'. | 'Okay, I'll leave it as Reading.' | 'Okay, I kept Piranesi.' (sounds like it nearly removed it). | The decline message was the generic 'Okay, I kept X.' | Follow-up offers can say what 'no' means (general core hook): 'Okay, Piranesi stays as Reading.' | backend/src/modules/assistant/domain/DomainPack.ts, backend/src/modules/assistant/AIRuntime.ts, backend/src/modules/assistant/domains/books/pipeline/replies.ts |  | Fixed
1 | R1-16 | First impression onboarding | polish | No forgot-password, no import of an existing history | Login and register pages; Settings. | Forgot password; Goodreads/StoryGraph import. | Neither exists. | Password reset needs email delivery (none configured); importing other platforms is SRS §37, which needs product approval. | Not built. A first-run welcome now explains the three ways to start (add, read/log, assistant). | frontend/src/features/library/LibraryPage.tsx |  | Won't fix (needs approval)
1 | R1-17 | Look and feel | polish | Sidebar scrolls away on long pages | Scrolled a long book page on desktop. | Navigation and Sign out stay in reach. | The sidebar scrolls with the content. | Sidebar wasn't sticky. | Sticky full-height sidebar on desktop. | frontend/src/components/layout/AppShell.tsx |  | Fixed
2 | R2-01 | Notes highlights reviews | major | Highlights are saved but never drawn on the page text | Paginated mode, selected a passage, chose green; reopened the book. | The passage shows green highlighting. | Listed in the Highlights panel, but the text stays plain. | Highlights were stored with their text and chapter but the reflowed pages were plain strings; nothing located the saved text on a page. | Each page now keeps the character offsets of its text, saved highlights are found in the chapter (forgiving line breaks) and drawn in their colour, stronger on light paper. | frontend/src/features/reader/flow-layout.ts, frontend/src/features/reader/FlowReaderPage.tsx |  | Fixed
2 | R2-02 | Reading experience | major | Reflowed text has no paragraph breaks and repeats each chapter title | Opened the novella and turned pages. | Proper paragraphs; title once. | Each chapter is one block starting 'The Last Lantern The Last Lantern Aldmere had...' under a heading saying the same. | EPUB extraction stripped every tag and collapsed whitespace, so <title> + <h1> + paragraphs became one run ('The Last Lantern The Last Lantern Aldmere...'). | Body only, one paragraph per block element, entities decoded, a heading that repeats the chapter title dropped; chapter graph v4 re-indexes existing books. | backend/src/modules/reader/epub-indexer.ts, backend/src/modules/reader/chapter-graph.ts |  | Fixed
2 | R2-03 | Assistant chat | major | 'dnf'd klara' added a different book | 'dnf'd klara, the robot pov wasnt for me' with Klara and the Sun owned. | Mark Klara and the Sun DNF, or ask. | 'I've added Klāre by Otto Hinnerk to your library as Did Not Finish.' | 'klara' covered 1 of 4 title words (score 75 < 80), so it wasn't treated as the owned book and the auto-add searched the catalogue. | A title's opening words name it (score 88); a near match to an owned title never auto-adds a stranger's book, the tool asks instead. | backend/src/modules/assistant/domains/books/text/match.ts, backend/src/modules/assistant/domains/books/pipeline/planChecks.ts |  | Fixed
2 | R2-04 | Tracking journal statistics | major | Reflection 'Save' after a session does nothing | Reader X > typed a reflection > Save (x3). | Saves and closes. | Dialog stays open, no message; the reflection never reaches the Journal. | Save sent the end call again with a reflection; the server treated the already-ended session's new reflection as 'different data' (409) and the error was swallowed. | A reflection can follow the end (only when none exists); errors are shown; Save/Skip return to the book page. | backend/src/modules/reading-sessions/reading-sessions.service.ts, frontend/src/features/reader/FlowReaderPage.tsx, frontend/src/features/reader/ReflectionPrompt.tsx |  | Fixed
2 | R2-05 | Tracking journal statistics | major | A stale reader session blocks new sessions with a developer-style error | Left the reader by navigating away; later 'Start a reading session' on another book. | Start a timer, or offer to end the old one. | 'Another session is already active for this user' and nothing shows or ends it. | Leaving the reader without closing it left the session ACTIVE; the 409 text was developer wording with no way out. | Leaving the reader pauses its session; the clash names the book ('You're still in a reading session for ...') and offers 'Pause that one and start here'. | frontend/src/features/reader/FlowReaderPage.tsx, frontend/src/features/library/SessionConflict.tsx, backend/src/modules/reading-sessions/reading-sessions.service.ts |  | Fixed
2 | R2-06 | Tracking journal statistics | major | Session time includes time away from the reader | Left the reader open in the background, came back, closed it. | Only active reading time. | '6 min of reading' for about a minute. | Duration was end minus start, including time away. | Sessions record paused time (pausedAt, pausedSeconds); a hidden tab pauses and resumes; the idle sweep pauses from the last page turn; paused time is subtracted. | backend/prisma/schema.prisma, backend/src/modules/reading-sessions/*, frontend/src/features/reader/FlowReaderPage.tsx |  | Fixed
2 | R2-07 | Tracking journal statistics | major | Journal shows a raw internal position | Journal after a reader session. | 'Chapter 4, 67%'. | '6 min · EPUB · epubcfi(/6/2!/4/2/1:0) → ch4' | The journal printed stored positions (CFI, chapter ids) as-is. | Entries carry startLabel/endLabel: chapter titles (from the chapter graph, CFIs by spine step), 'p. N' for pages. | backend/src/modules/journal/journal.service.ts, frontend/src/features/journal/JournalPage.tsx |  | Fixed
2 | R2-08 | Reading experience | major | Can't select text in the default 3D Flip mode | Drag-select and double-click in 3D Flip. | Text selects; highlight popover appears. | Dragging starts a page curl; only works after switching to Paginated, with no hint. | react-pageflip took mouse and touch input in 3D Flip mode, so a drag curled the page instead of selecting. | The flipbook no longer takes pointer input: text selects in every mode; pages turn with the buttons, arrow keys or a swipe. | frontend/src/features/reader/FlowReaderPage.tsx |  | Fixed
2 | R2-09 | Reading experience | major | Phone reader shows ~6 lines in a tiny inset card | Mobile 375x812, reader. | Text fills the screen. | Small inner card, ~6 lines per page; bookmark and View Original missing from the toolbar. | Pages were always A4 halves of a two-page spread, tiny on a phone; ten toolbar icons overflowed. | Below 768px one page fills the screen; Note, Translate, Music, View Original and 'Not where you left off?' move into a More menu. | frontend/src/features/reader/FlowReaderPage.tsx, frontend/src/features/ai/TranslatePanel.tsx |  | Fixed
2 | R2-10 | Book page and details | major | Rating and Favourite silently lost without 'Save review' | Clicked 5 stars and Favourite, refreshed. | Saved instantly or warned. | All empty after refresh; no 'Saved' confirmation even when saving works. | Stars and Favourite only changed the form; nothing saved until 'Save review'. | Rating, favourite and reread save on click with a 'Saved.' note; unsaved review text is kept. | frontend/src/features/reviews/ReviewPanel.tsx |  | Fixed
2 | R2-11 | Speed reliability | major | Logged out on refresh mid-session | ~6 min after sign-in, refreshed the reader. | Stay signed in. | Sent to /login, then landed on Library. | Refresh tokens rotate on every use; two refreshes with the same cookie (StrictMode's double restore, parallel 401s, several tabs reloading) made the loser look like token reuse and signed the reader out. | One refresh at a time: shared within a tab and serialised across tabs with a Web Lock; a failed refresh never clears a newer token. | frontend/src/lib/api/client.ts, frontend/src/lib/auth-context.tsx |  | Fixed
2 | R2-12 | Reading experience | minor | Changing font size resets to the start | Page 2 of 8 > font +2. | Same passage. | 'Page 1 of 10', back at chapter 1. | Re-pagination re-anchored to the chapter's first page, and the flipbook wasn't remounted at the new index. | Position is chapter + character offset; after any re-layout the reader lands on the page holding that passage. | frontend/src/features/reader/FlowReaderPage.tsx, frontend/src/features/reader/flow-layout.ts |  | Fixed
2 | R2-13 | Reading experience | minor | 'View Original' loses your place and has no way back | At 67% > View Original. | Same position; toggle back. | Opens at chapter 1, 0%; no side padding, default Times; only Close. | The original view ignored the reading view's position (epub.js only finds an idref with '#') and had only Close. | Opens at the chapter you were on; 'Back to reading view' button. | frontend/src/features/reader/ReaderPage.tsx, frontend/src/features/reader/EpubReader.tsx |  | Fixed
2 | R2-14 | Reading experience | minor | Reader renders shrunken after closing a session | X > Session ended > Skip. | Back to the library, or a normal reader. | A small card mid-screen; X vs Skip inconsistent. | The reflection prompt replaced the reader, and Save/Skip went 'back' in history, sometimes into the reading view of the ended session. | The prompt sits over the book; both readers return to the book page afterwards. | frontend/src/features/reader/FlowReaderPage.tsx, frontend/src/features/reader/ReaderPage.tsx |  | Fixed
2 | R2-15 | Reading experience | minor | Pages half empty; first spread's left page blank | Read the first spreads on desktop. | Pages fill. | Text stops two-thirds down; next spread has one line then a new chapter. | Pagination estimated characters per page (deliberately conservative) and the first page was laid out as a lone 'cover'. | Pages are measured with the real fonts in an offscreen copy of the page (about 97% full, nothing clipped); the cover slot is used only for a real cover. | frontend/src/features/reader/flow-layout.ts, frontend/src/features/reader/FlowReaderPage.tsx |  | Fixed
2 | R2-16 | Reading experience | minor | 'mins left' estimate depends on layout | Changed font size, chapter list, mobile. | Stable estimate. | ~32, ~40, ~68, ~50 at the same spot. | 'mins left' was pages left x 4. | Progress and time left come from characters read (about 230 words a minute), the same at any font size. | frontend/src/features/reader/FlowReaderPage.tsx, frontend/src/features/reader/ReaderProgressScrubber.tsx |  | Fixed
2 | R2-17 | Reading experience | minor | Arrow keys don't turn pages | Right arrow in the reader. | Next page. | Nothing. | No keyboard handling in the reading view. | Left/Right arrows and Page Up/Down turn pages (not while typing or in a dialog). | frontend/src/features/reader/FlowReaderPage.tsx |  | Fixed
2 | R2-18 | Notes highlights reviews | minor | Reader highlights/notes absent from the book page; no central notes view | Highlight with a margin note > book page. | Listed on the book page. | 'Notes: No notes yet.' | The book page listed notes only; highlights lived in the reader. | 'Highlights & quotes' on the book page, newest first, with colour, margin note and a link back into the book. (A separate all-books notes page isn't built.) | frontend/src/features/notes/BookHighlights.tsx, frontend/src/features/library/BookDetailPage.tsx |  | Partly fixed
2 | R2-19 | Assistant chat | minor | Natural follow-ups and phrasing variants fail | 'finsihed circe, 4 stars and put it on comfort reads', 'put it on comfort reads', 'put circe on comfort reads', 'actually undo that'. | Handled, or each simple command. | The same canned 'not set up' reply each time; a message typed while pending wasn't sent on Enter. | 'put X on Y' needed the word 'shelf'; 'it' was bound to the previous turn's subject; 'actually undo that' wasn't recognised. | Shelves named without 'shelf' (and 'add X to Y' when Y is a shelf or X is theirs); 'it' is the book named in the same message; undo accepts fillers. The tester's sentence now does status, rating and shelf without a model. | backend/src/modules/assistant/domains/books/conversation/quickCommands.ts, backend/src/modules/assistant/domains/books/pipeline/preRoute.ts, backend/src/modules/assistant/domains/books/pipeline/undo.ts |  | Fixed
2 | R2-20 | Tracking journal statistics | minor | No finish dates, so 'this year' can't be answered | Marked books Finished; asked 'how many books did i read this year'. | Finish dates; yearly count. | 'Bunko can only tell which were this year from logged reading sessions...' | No completion date was stored. | UserWork.finishedAt (SRS §18.2), set when marked Finished, backfilled from the last session; shown on the book page; 'this year' uses it. | backend/prisma/schema.prisma, backend/src/modules/library/library.service.ts, backend/src/modules/assistant/domains/books/conversation/libraryAnswers.ts, frontend/src/features/library/BookDetailPage.tsx |  | Fixed
2 | R2-21 | Library adding finding books | minor | Book search slow and typo-intolerant | 'tomorow and tomorrow and tomorrow'. | Right book within a couple of seconds. | 10-15s spinner, unrelated results. | Catalogue providers are slow on a cold query and have no fuzzy matching; results are cached for an hour after the first search. | Not changed this round (needs a provider-side change). |  |  | Open
2 | R2-22 | Library adding finding books | minor | Status doesn't follow reading; no progress shown | Read to 67%, back to Library. | Status Reading; progress on the card. | Still Want to Read; no progress; 'Continue Reading' before ever opening. | Opening a book never changed its status; the button always said 'Continue Reading'. | Starting or logging a session moves Want to Read to Reading (never Finished/DNF); 'Start reading' until the first session. (Progress on cards not built.) | backend/src/modules/library/library.service.ts, backend/src/modules/reading-sessions/reading-sessions.service.ts, frontend/src/features/library/ContinueReadingButton.tsx |  | Partly fixed
2 | R2-23 | Tracking journal statistics | minor | Languages 'Unknown 6' and lowercase 'english'; EPUB reading added no pages | Statistics > Languages. | 'English'; EPUB pages counted. | 'Unknown 6 books', 'english 1 book'; pages read only from the manual log. | The page passed language names through Intl.DisplayNames, which reads 'english' as a valid code and returns it lowercased; books with no language said 'Unknown'. | Only codes are looked up, names are capitalised; missing language reads 'Not recorded'. (EPUB pages need a start position; unchanged.) | frontend/src/features/statistics/chart-format.ts, frontend/src/features/statistics/StatisticsPage.tsx |  | Partly fixed
2 | R2-24 | Shelves organizing | minor | An empty shelf offers no way to add books | New shelf '2026 faves'. | An 'Add books' picker. | Text only, no button. | No way to add books from a shelf. | 'Add books' on custom shelves and in the empty state: a searchable picker of library books. | frontend/src/features/shelves/AddToShelfDialog.tsx, frontend/src/features/shelves/ShelvesPage.tsx |  | Fixed
2 | R2-25 | Shelves organizing | polish | Low-contrast toggle and unlabeled shelf tabs | Shelves page. | Readable toggle; named tabs. | 'Covers' dark brown on near-black; tabs read as unnamed buttons; odd brown scrollbar strip. | Inactive toggle text at 70% opacity on near-black; dark wood scrollbar on the paper background. | Full-strength toggle text; shelf tabs say their name and count and report pressed state; light paper scrollbar. | frontend/src/features/shelves/ShelvesPage.tsx, frontend/src/index.css |  | Fixed
2 | R2-26 | Tracking journal statistics | polish | Journal order wrong; entries can't be edited | Logged a session after another the same day. | Newest first; edit/delete. | Newer entry below the older; clicking opens the book. | Journal sorted by start time, so a session logged after the fact sorted by when it began. | Sorted by when sessions ended. (Editing an entry isn't built.) | backend/src/modules/journal/journal.service.ts |  | Partly fixed
2 | R2-27 | Book page and details | polish | Duplicate status, marketing-blurb synopsis, small icon issues | Book pages and reader toolbar. | One status control, clean synopsis, labelled icons. | Pill plus dropdown; synopsis starts with press quotes; unlabeled icon; bookmark icon never fills. | Status showed as a pill and a dropdown; catalogue copy opens with press quotes; bookmark icon never reflected state. | One labelled status control; leading press quotes and ALL-CAPS banners trimmed for display; the bookmark fills when the chapter is bookmarked. | frontend/src/features/library/BookDetailPage.tsx, frontend/src/features/library/synopsis.ts, frontend/src/features/reader/FlowReaderPage.tsx |  | Fixed
2 | R2-28 | First impression onboarding | polish | No import or account basics for switchers | Welcome screen and Settings. | Import, yearly goal, export, change password. | None present. | Import (SRS §37), reading goals, export and password change aren't in the MVP scope. | Not built; needs product approval. |  |  | Won't fix (needs approval)
3 | R3-01 | Notes highlights reviews | major | Saved review is blank after a page refresh, and Save invites wiping it | Write a review, Save changes ('Saved.'), refresh the page. | Review text still there. | Box empty with Save enabled; in-app navigation shows it again. | Regression from R2-10: the panel moved its 'last saved text' marker before React ran the state update, so on a fresh load the update compared against the new text and kept the empty draft. | The previous value is captured before the marker moves; verified: text survives a refresh and Save stays disabled until edited. | frontend/src/features/reviews/ReviewPanel.tsx |  | Fixed
3 | R3-02 | Shelves organizing | major | Spine language badge reads 'JAP' | Shelves > Spines, a book marked Japanese. | A neutral code or no badge. | 'JAP' on the spine, an ethnic slur. | Spines printed the first three letters of the language name. | Two-letter ISO codes (JA, TA, ID); no badge when the language isn't known. | frontend/src/lib/language-code.ts, frontend/src/features/shelves/BookSpine.tsx |  | Fixed
3 | R3-03 | Library adding finding books | major | Original language wrong in search results and on the book | Add a book > search 'piranesi', 'Convenience Store Woman'. | Piranesi original English; Murata original Japanese. | Every Open Library result 'Orig: Japanese'; Google Books Murata 'Orig: English'; carried into Shelves and Statistics. | Book search filled in 'Japanese' as the original language whenever a catalogue didn't give one (Google's edition language was also used as the original). | Original language is left empty unless known; a migration clears the guessed value on existing books (where the edition isn't Japanese and the title has no Japanese script). | backend/src/modules/metadata/metadata.service.ts, backend/prisma/migrations/20261023090000_clear_guessed_original_language |  | Fixed
3 | R3-04 | Assistant chat | major | Assistant added a foreign-language edition of Circe | 'I just finished Circe by Madeline Miller, 4 stars'. | The English edition. | Indonesian description, 'IND' spine, Indonesian in Statistics. | Two editions with the same title and author were de-duplicated first-come, and the Indonesian one arrived first. | De-duplication and ranking prefer the reader's language for Latin-script queries (other scripts unaffected). | backend/src/modules/metadata/metadata.service.ts |  | Fixed
3 | R3-05 | Book page and details | minor | Description shows raw markdown | Piranesi's book page. | Formatted or plain text. | '**From the *New York Times* bestselling author...**' with asterisks. | Some catalogues send markdown emphasis. | Shown as plain text (bold/italic markers removed; arithmetic asterisks left alone). | frontend/src/features/library/synopsis.ts |  | Fixed
3 | R3-06 | Tracking journal statistics | minor | Active paper session disappears on refresh | Start a reading session, refresh. | Still in progress, with elapsed time. | 'Start a reading session' again; no timer while running. | The paper-session panel only remembered its session in page state. | GET /reading-sessions/open restores it after a refresh; the panel shows 'Reading for N min · started 4:05 PM'. | backend/src/modules/reading-sessions/*, frontend/src/lib/api/sessions.ts, frontend/src/features/library/PhysicalSessionPanel.tsx |  | Fixed
3 | R3-07 | Assistant chat | minor | Natural phrasing becomes part of the title | 'gave up on Klara and the Sun around halfway, it just wasn't for me'. | Klara and the Sun marked DNF. | 'I couldn't find a book called Klara and the Sun around halfway' with unrelated alternatives. | After the comma was cut, 'around halfway' stayed in the title. | How-far phrases (halfway, page 120, 40%...) are dropped, and when one of the reader's titles opens the phrase, that title is used. | backend/src/modules/assistant/domains/books/conversation/quickCommands.ts |  | Fixed
3 | R3-08 | Shelves organizing | minor | Shelf controls nearly invisible on dark wood | Shelves: Covers/Spines toggle and Add books. | Readable controls. | Dark text on dark brown. | The controls used wood-100, a colour step the palette doesn't define, so the class produced nothing; paper-600 and some moss steps (used in 36 files) were missing too. | Undefined shades replaced; paper-600, moss-200/400/800 added to the palette and DESIGN.md. | frontend/src/features/shelves/ShelvesPage.tsx, frontend/tailwind.config.js, DESIGN.md |  | Fixed
3 | R3-09 | Tracking journal statistics | minor | Journal entries can't be edited or deleted | Try to remove an accidental 1-minute session. | Edit or delete per entry. | Entries only link to the book. | No delete for sessions. | Delete (with confirmation) on each journal entry: DELETE /reading-sessions/:id, finished sessions only; highlights and notes from it stay. | backend/src/modules/reading-sessions/*, frontend/src/features/journal/JournalPage.tsx, frontend/src/lib/api/journal.ts |  | Partly fixed
3 | R3-10 | First impression onboarding | minor | No Goodreads/StoryGraph import | Settings and empty Library. | CSV import. | None. | Importing other platforms is SRS §37 (needs product approval). | Not built. |  |  | Won't fix (needs approval)
3 | R3-11 | Assistant chat | polish | Contradictory status confirmation | 'started The Left Hand of Darkness yesterday'. | 'Added as Reading.' | 'I've added ... as Want to Read. I've marked ... as Reading.' | The merged 'added as X' reply didn't match authors with initials ('Ursula K. Le Guin'). | The author part may contain periods; one sentence now. | backend/src/modules/assistant/domains/books/pipeline/replies.ts |  | Fixed
3 | R3-12 | Look and feel | polish | Developer-ish or inconsistent wording | Shelves, Add book, Settings. | Consistent reader language. | 'Catalog Racks & Collections:', 'All Volumes' vs 'All Books', 'To Read', 'Parts Count', 'Your Added Language', source badges, 'search vectors', consent named differently on two pages. | Labels written from the code's point of view. | 'Your shelves', 'All books', 'Want to Read', 'Parts'/'Chapters', 'Language you read it in', no source badges, 'a private search index', and the setting renamed 'Assistant and book summaries' to match the Assistant page. | frontend/src/features/shelves/ShelvesPage.tsx, frontend/src/features/library/AddBookDialog.tsx, frontend/src/features/ai/ai-disclosure.ts, frontend/src/features/ai/AiSettingsCard.tsx |  | Fixed
3 | R3-13 | Library adding finding books | polish | Manual add lacks status; adding a copy gives no feedback | Add custom book manually; Add a copy > Physical copy. | Status choice; confirmation. | Silently Want to Read; no feedback. | The manual form had no status choice; adding a copy closed silently. | 'Add it as' on the manual form too; 'Copy added. You can start reading it now.' (Page count isn't stored on a work.) | frontend/src/features/library/AddBookDialog.tsx, frontend/src/features/library/BookQuickActionModal.tsx |  | Partly fixed
3 | R3-14 | Tracking journal statistics | polish | Statistics filler | Statistics with no EPUBs and no genres. | Caveats only when relevant. | 'EPUB pages are estimated' with no EPUBs; a lone 'No genre: 5' bar. | Caveat always shown; an all-unknown breakdown drew one bar. | The EPUB caveat appears only with EPUB reading; 'None of your books has a genre recorded yet.' (Yearly goals and a ratings chart aren't in the SRS.) | frontend/src/features/statistics/StatisticsPage.tsx, frontend/src/features/statistics/BreakdownList.tsx |  | Partly fixed
3 | R3-15 | Book page and details | polish | Review buttons shown with only a rating | Rate a book with no review text. | 'Remove review' hidden until a review exists. | Both buttons present. | The review buttons showed whenever a review row existed, including rating-only. | They appear only once there is review text. | frontend/src/features/reviews/ReviewPanel.tsx |  | Fixed
4 | R4-01 | Notes highlights reviews | major | Deleting one highlight also deleted another and its margin note | Reader > Highlights (3) > trash on the Quote, no feedback, click again. | Only the Quote deleted, with confirm or undo. | The Quote and the yellow highlight with its margin note both gone; no confirmation or feedback. | Deleting waited for the server before the list changed, so a second click landed on the next highlight as it slid up. | Highlights leave the list at once (restored if the delete fails), and deleting asks in place: Delete / Keep. | frontend/src/features/reader/AnnotationsDrawer.tsx, frontend/src/lib/api/annotations.ts |  | Fixed
4 | R4-02 | Reading experience | major | Current chapter wrong: footer, chapter list, bookmarks, notes | Turn pages with arrows in 3D Flip / scroll; bookmark in The Customs House; 'This chapter' note in A Ledger in Salt. | Everything names the chapter being read. | Footer lags 1-2 chapters; bookmark labelled and jumping to the wrong chapter; note saved as 'Chapter · ch1'. | The page-flip handler was memoised on the first render, before chapters loaded, so the chapter name never followed page turns; notes showed the stored chapter id. | The flip handler goes through a ref to the latest code; the chapter name is derived from the current chapter; notes carry positionLabel (the chapter title). | frontend/src/features/reader/FlowReaderPage.tsx, backend/src/modules/notes/notes.service.ts, backend/src/modules/reader/position-labels.ts |  | Fixed
4 | R4-03 | Reading experience | major | Scroll mode doesn't reopen where you left off | Scroll mode, go to The Customs House (~58%), refresh. | Reopens there. | Top of chapter 1 at 0% while the footer says another chapter. | Scroll mode tried to scroll before its chapters were on screen, and tracked position with requestAnimationFrame, which stalls in a background tab, so offsets stayed at 0. | Position is chapter + offset in scroll mode too, restored once the chapters render; tracking uses a timer. | frontend/src/features/reader/FlowReaderPage.tsx |  | Fixed
4 | R4-04 | Reading experience | major | View Original's first chapter broken; switching views loses place | At A Ledger in Salt, View Original, then Back to reading view. | Same spot, normal layout, place kept. | Huge heading, paragraphs in 4-5 narrow columns, opens at chapter 1, 0% / '20 min left'; back in reading view at 0%; ~2s blank page per turn; no highlights. | The original-file view treated the first section of any book as a cover (narrow columns); position loss came from R4-03; the time estimate was guessed from chapter counts. | Only a section marked as a cover is laid out as one; the place carries both ways; no time guess in the original view. (Page-turn blanking and highlights in the original view unchanged.) | frontend/src/features/reader/EpubReader.tsx, frontend/src/features/reader/ReaderPage.tsx |  | Partly fixed
4 | R4-05 | Book page and details | major | Finish date can't be set or changed | Finish a book; add as 'Already read'; 'finally finished circe last night, 4 stars'. | Editable date; 'last night' = yesterday. | Plain text; 'Already read' stamps today (inflating this year's count); Circe got today. | finishedAt could only be 'now'; 'Already read' dated today; the assistant ignored 'last night'. | Editable 'Finished on' date (PATCH /works finishedAt, no future dates); 'Already read' starts undated; 'finished X last night' dates it yesterday and says so. | backend/src/modules/library/*, frontend/src/features/library/BookDetailPage.tsx, frontend/src/features/library/AddBookDialog.tsx, backend/src/modules/assistant/domains/books/actions/libraryTools.ts, backend/src/modules/assistant/domains/books/conversation/quickCommands.ts |  | Fixed
4 | R4-06 | Reading experience | minor | Search result jumps to the chapter, not the match | Search 'ledger', click a result. | Scroll to and mark the match; search box focused. | Top of chapter, nothing marked; first typing lost. | Search results carried only the chapter; the box wasn't focused. | Jumps to the page with the match, marks the words for a few seconds; the box is focused. | frontend/src/features/reader/FlowReaderPage.tsx, frontend/src/features/reader/InBookSearchDrawer.tsx |  | Fixed
4 | R4-07 | Reading experience | minor | No end-of-book moment | Read to 100%. | Offer to mark finished / rate. | Nothing; '1 min left' at 100%; status stays Reading. | No handling of the last page. | 'The end. Finished <title>?' with Mark as finished; 'Last page' instead of '1 min left'. | frontend/src/features/reader/FlowReaderPage.tsx, frontend/src/features/reader/ReaderProgressScrubber.tsx |  | Fixed
4 | R4-08 | Library adding finding books | minor | Add-book search slow, labels confusing | Search 'The Housekeeper and the Professor'. | Fast results, clear labels. | ~16s; 'Added: English' badge on every result; leading 'The' dropped. | Coloured chips per result ('Added: English' meant the language you'd read it in). | One quiet line ('Originally Japanese · 14 chapters'), synopsis cleaned. (Catalogue speed unchanged.) | frontend/src/features/library/AddBookDialog.tsx |  | Partly fixed
4 | R4-09 | Library adding finding books | minor | Library search can't combine author and title; no metadata editing | Search 'ishiguro klara'; try to fix an author/cover. | Finds the book; an Edit option. | No match; no edit; inconsistent placeholder covers. | Library search matched the whole phrase against title or author. | Each word must match the title or an author. (Editing book details isn't built: works are shared catalogue entries.) | backend/src/modules/library/library.service.ts |  | Partly fixed
4 | R4-10 | Book page and details | minor | 'Open the book' on a highlight doesn't go to it | Book page > Highlights > Open the book. | Opens at that highlight. | Opens at the last position. | The link opened the book at the last position. | 'Read it in the book' opens the reader at that highlight. | frontend/src/features/notes/BookHighlights.tsx, frontend/src/features/reader/FlowReaderPage.tsx |  | Fixed
4 | R4-11 | Notes highlights reviews | minor | Highlights can't be edited from the page; weak feedback | Click a highlight; save one with a note or a Quote. | Edit/recolour/delete on click; confirmation. | Nothing on click; no confirmation; toolbar covers the selection; quotes cut off; raw colour names. | Highlights on the page weren't interactive; saving was silent. | Tapping a highlight opens your highlights; 'Highlight saved' / 'Quote saved' notice; colour labels replaced by a swatch. | frontend/src/features/reader/FlowReaderPage.tsx, frontend/src/features/reader/AnnotationsDrawer.tsx |  | Fixed
4 | R4-12 | Reading experience | minor | Dark theme leaves light surfaces | Appearance > Dark. | Whole reader dark. | Progress bar and Appearance panel stay cream; stray horizontal scrollbar. | The progress bar used fixed cream colours. | It takes the reading theme's colours. (The Appearance panel stays light.) | frontend/src/features/reader/ReaderProgressScrubber.tsx |  | Partly fixed
4 | R4-13 | Reading experience | minor | Menus don't close with Escape or an outside click | Open the bookmarks dropdown or the phone '...' menu. | Closes. | Stays open; two menus open at once. | No Escape or outside-click handling. | Escape closes menus and panels; clicking outside closes the dropdowns. | frontend/src/features/reader/FlowReaderPage.tsx |  | Fixed
4 | R4-14 | Tracking journal statistics | minor | Tiny accidental sessions; inconsistent page fields | Open and close a book within a minute; compare Log reading and ending a timed session. | Very short visits not logged; same page fields. | 'Under a minute' sessions counted; free-text vs numeric page fields. | Every opened reader session was kept. | Closing a book within a minute leaves no journal entry. (The paper-session form still asks for a chapter or page as text, which SRS §12.9 requires.) | frontend/src/features/reader/FlowReaderPage.tsx |  | Partly fixed
4 | R4-15 | Assistant chat | minor | Natural shelf request answered with a list | 'can you put klara on my comfort reads shelf'. | Adds it or asks. | Listed the shelf; 'something like piranesi' ignored. | 'can you ...' read as a question, so it was answered from the library. | Polite requests ('can you put ...?') are commands. | backend/src/modules/assistant/domains/books/pipeline/preRoute.ts |  | Fixed
4 | R4-16 | Look and feel | polish | Developer-ish text and cramped phone layouts | Desktop and phone. | Reader wording, tidy phone layouts. | 'CHAPTERS / TOC', 'Chapter · ch1', 'Drag, or use the keyboard' on phone, small chapter titles, cramped Editions header and Journal dates, full-screen Appearance sheet. | Leftover technical labels; fixed heading size; dates squeezing journal entries on phones. | 'Chapters', plainer shelves subtitle, chapter titles a step above body text, journal dates above the title on phones. | frontend/src/features/reader/ReaderPage.tsx, frontend/src/features/shelves/ShelvesPage.tsx, frontend/src/features/reader/FlowReaderPage.tsx, frontend/src/features/journal/JournalPage.tsx |  | Partly fixed
4 | R4-17 | Speed reliability | polish | Blank spinner on every full page load | Refresh any page. | App shell immediately. | 1-2s blank page; typing lost; 'Maximum update depth exceeded' and some 404s in the console. | The app waits for the session to be restored before drawing anything. | Not changed this round. |  |  | Open
5 | R5-01 | Shelves organizing | blocker | "Add book" button in the Shelves page's "Add books to [shelf]" dialog does not work | Shelves > created a new shelf 'rainy day reads' via '+ New Shelf' > clicked 'Add books' on the empty shelf > checked Circe and Piranesi > clicked 'Add book' (repeated with ref clicks, coordinate clicks, and Enter while focused). | Selected books get added to the shelf and the dialog closes/updates the count. | Nothing happens -- dialog stays open, shelf still shows '0 books'. Workaround: toggling the shelf tag on each book's own detail page works correctly. |  |  |  |  | Open
5 | R5-02 | Tracking journal statistics | major | Reflection typed into the reader's "Session ended" dialog is never saved | Finished 'The Lantern Keeper of Aldmere' in the reader > 'Close the book' > 'Session ended / 6 min of reading. Nice work.' dialog > typed a reflection > Save. | The reflection text appears in the Journal entry, the book's Notes, or its Review. | The reflection text is gone entirely. The Journal entry shows an unrelated earlier highlight instead; Notes/Review stay empty even after reload. |  |  |  |  | Open
5 | R5-03 | Tracking journal statistics | minor | Logged reading session date is off by one day | Journal > 'Log reading' > book Piranesi, Day field showed '28-10-2026' (today), Minutes 45, From page 10, To page 55, reflection text, 'Log reading'. | Journal entry shows 'Oct 28, 2026' matching the selected date. | Entry is listed under 'Oct 27, 2026' -- one day earlier, suggesting a timezone conversion bug. |  |  |  |  | Open
5 | R5-04 | Assistant chat | major | Off-topic assistant questions reliably time out (even on retry) | In Assistant chat, after several successful book-related exchanges, sent 'whats the weather like today'. Waited 30s -> timeout message. Clicked 'Try again', waited another 30s. | Either a quick graceful redirect, or at least a successful retry. | Both the original attempt and the retry timed out after ~30s each with the same message. A normal on-topic question sent right after answered correctly within ~10s, so the failure seems specific to off-topic prompts. |  |  |  |  | Open
5 | R5-05 | Assistant chat | minor | Natural phrasing "i started reading circe" fails to resolve the book despite Circe being in the library and just discussed | After being recommended 'Circe by Madeline Miller' in the previous message, typed 'i started reading circe'. | The assistant recognizes 'circe' as the book just discussed and marks it Reading. | "I couldn't find a book called 'reading circe'..." -- it matched the whole phrase as a title instead of parsing 'started reading' as the verb phrase. Retyping with the full title worked. |  |  |  |  | Open
5 | R5-06 | Speed reliability | major | Unexpected full session logout with no warning, not reproduced on retry | On a book detail page (The Name of the Wind), clicked 'Add note', typed a note, clicked the '+ Add note' trigger button. | Note dialog opens or note saves; if a session genuinely expired, a clear message should explain why. | The app silently navigated to /login with all session state lost, no toast or explanation. Logging back in and repeating the exact steps worked fine every subsequent time. |  |  |  |  | Open
5 | R5-07 | Look and feel | minor | Toolbar tooltip/panel overlays get stuck open and block clicks underneath | In the reader, clicked the Translate icon (shows 'isn't set up on this server yet' tooltip), then clicked other toolbar icons or chapter-list entries without first dismissing the Translate tooltip. | Clicking elsewhere should dismiss the previous tooltip automatically, or at least not intercept the click. | The tooltip stays on top, intercepting clicks meant for elements beneath it. Escape or its own close button dismisses it, but a casual user wouldn't know to do that and would think the buttons are broken. |  |  |  |  | Open
5 | R5-08 | Library adding finding books | minor | Library grid cover art falls back to a generic placeholder even when real cover art exists | Added 'The Name of the Wind' via the Assistant, then viewed the Library grid. | Since the book's detail page and quick-view popup both show real cover art, the grid thumbnail should match. | The Library grid shows a generic orange 'T' placeholder tile, while every other metadata field is correctly enriched. |  |  |  |  | Open
5 | R5-09 | Tracking journal statistics | polish | Settings page AI-features copy contradicts actual working behavior | Settings > 'AI features' section. | Messaging consistent with the Assistant chat being clearly live and working with a real AI model. | Footer text reads "AI features aren't set up on this server yet -- your choice is saved for when they are", which is stale and could confuse a user about whether their data is actually being sent anywhere. |  |  |  |  | Open

## Round 1
Round 1 | 2026-10-23 | Meera, book-lover persona (code-blind agent; browser only)
Local: frontend :5174, API :3100 with AI_PROVIDER=nvidia but no NVIDIA_API_KEY yet; Claude ai-service not running. Seeded account with 6 books (one sample EPUB).
Area | Score | Tester's reason
First impression onboarding | 6 | Calm, bookish login with a clear error, but no forgot-password, onboarding or import, and the first library screen shows wrong covers.
Library adding finding books | 5 | Exact search works and doesn't duplicate, but a single typo gives junk, search takes 6-8s, covers are wrong, there's no sort and no status choice when adding.
Book page and details | 5 | Tidy single screen, but no description, pages or publication info, no way to fix a cover, and modal buttons that do nothing.
Reading experience | 2 | The sample EPUB couldn't be opened from any path.
Tracking journal statistics | 4 | Timer-only sessions, pages not counted, journal entries don't name the book, stats contradict themselves.
Shelves organizing | 6 | Charming bookcase and inline shelf creation, but odd one-book rows, per-row scrollbars, an inverted toggle and overlapping arrows on mobile.
Notes highlights reviews | 6 | Fast and pleasant, but whole stars only, notes undated, and highlights impossible without the reader.
Assistant chat | 4 | Good when phrased exactly, but about half the messages failed with 'An unexpected error occurred'; it can't handle 'it' or typos, and it invented 'Dune II'.
Look and feel | 7 | Feels made by book people; wrong covers undercut it.
Speed reliability | 4 | Slow covers and search, status changes take ~3s with no feedback, assistant failures, remove seemed to do nothing.
Overall | 4 | Good bones and taste, but I can't read a book, covers are wrong, the journal doesn't name books, and the assistant fails half the time.
Issues and fixes
Round | ID | Area | Severity | Title | Steps | Expected | Actual | Root cause | Fix | Files | Commit | Status | Verified in round
1 | R1-01 | Reading experience | blocker | No way to open the digital reader, even for a book with an EPUB | Library > 'A Bunko Sample Book' > 'Open Digital Reader'; clicked the EPUB edition row; tried status Reading, reload, and 'Start / Resume Reading Session'. | The EPUB opens in the reader. | Every path lands on the book details page; the EPUB edition row has no read button. | QA seed attached the EPUB with the upload id instead of the stored file id, so no copy existed; and the app gave a digital edition without its file no way forward. | Seed fixed (uses the id /files/:id/confirm returns) and now ships an original 5-chapter novella. A digital edition with no file shows 'Upload file'; the quick-action modal only offers actions that work. | backend/scripts/seed-qa-reader.ts, backend/scripts/qa-sample-book.ts, frontend/src/features/library/BookDetailPage.tsx, frontend/src/features/library/AddEditionDialog.tsx, frontend/src/features/library/BookQuickActionModal.tsx |  | Fixed
1 | R1-02 | Library adding finding books | major | Most covers are for completely different books | Open Library (also Shelves, modal, book page). | The real cover for each book. | The Left Hand of Darkness and the sample book show 'Their Eyes Were Watching God'; Circe, Piranesi and Klara show unrelated books; a hand-added zine got a random cover. There's no way to change or remove a cover. | Three code paths took the first search result with any cover regardless of title; the seed also used guessed cover ids. Wikidata series discovery filed books under their own title. | Covers only from a result with the same main title and a shared author surname (pickMatchingCover), looked up in the background; self-named series ignored and cleared. Changing/removing a cover by hand is not built yet (covers live on the shared catalogue entry). | backend/src/modules/library/library.service.ts, backend/scripts/seed-qa-reader.ts |  | Partly fixed
1 | R1-03 | Assistant chat | major | Many assistant messages fail with a generic error | 'no i meant the zevin one...', 'I started Tomorrow, and Tomorrow, and Tomorrow' (the app's own example), 'ok i started the first one. and dnf'd circe tbh', 'and add it to my comfort reads shelf', 'rate it 5 stars actually'. | The change is made, or a clarifying question. | 'An unexpected error occurred' each time, no reason, no retry. Short single-book commands worked. | No NVIDIA key on the test server: NIM's 401 became a plain Error and surfaced as a 500. Separately, titles with commas, filler words ('ok', 'and', 'tbh', 'actually') and 'it' defeated the fast paths, so those messages needed the model. | Rejected key / rate limit are 'unavailable'; a missing key is detected at startup and answered with a plain message; any other failure is a friendly logged reply. Owned titles with commas are masked before clause splitting; filler words stripped. | backend/src/modules/assistant/clients/NvidiaNimClient.ts, backend/src/modules/assistant/aiController.ts, backend/src/modules/assistant/domains/books/conversation/quickCommands.ts |  | Fixed
1 | R1-04 | Assistant chat | major | A typo in an owned title makes it search the catalogue for junk | 'started tomorow and tomorrow last night, its so good already' (the book is in the library). | It matches the owned book. | "I couldn't find a book called \"tomorow\". The closest were \"Notes on the History of Fort George\"..." | Title matching needed exact words; the list splitter split 'tomorow and tomorrow' into two books. | Typo-tolerant word matching on owned titles; lists split only into books the reader owns. | backend/src/modules/assistant/domains/books/text/match.ts, backend/src/modules/assistant/domains/books/conversation/quickCommands.ts |  | Fixed
1 | R1-05 | Assistant chat | major | Recommendations made up a sequel and ignored 'something like Piranesi' | 'what should i read next? something like piranesi' | Books like Piranesi, and accurate facts. | Listed the Want to Read list only, and said 'the series continues with Dune II by Frank Herbert' (no such book). | The 'series continues' line came from a Wikidata lookup that returned non-books ('Dune II'); 'like X' wasn't used. | Series continuation removed; 'something like X' ranks the list by X's authors and genres with reasons, and asks the model for books beyond the list. | backend/src/modules/assistant/domains/books/actions/readTools.ts, backend/src/modules/assistant/domains/books/pipeline/preRoute.ts, backend/src/modules/assistant/domains/books/prompts/answerPrompt.ts |  | Fixed
1 | R1-06 | Tracking journal statistics | major | Journal entries don't say which book | Piranesi > physical edition > session > end with 'p 112' and a reflection > Journal. | Entry shows the book, page and time, and links to it. | 'Oct 23, 2026 · 0 min · “the other is kinda sus now”': no title, no page, not clickable; no way to add an entry from the Journal. | Journal entries carried no book. | Each entry names and links its book with its cover and format; 'Log reading' on the Journal. | backend/src/modules/journal/journal.service.ts, frontend/src/features/journal/JournalPage.tsx |  | Fixed
1 | R1-07 | Tracking journal statistics | major | Reading can only be logged live, and pages aren't counted | Started and immediately ended a session with 'p 112'. | Log a past session (time, date, page), and pages count. | 'Session saved — 0 min. Nice reading.' Stats: 'Pages read 0'. No manual duration/date, no progress on the book, no finish date. | Only live timed sessions existed; a physical session with only an end page can't count pages. | POST /reading-sessions/log and a 'Log reading' form (book, day, minutes, from/to page, reflection) on the Journal and book page; both pages make them count. | backend/src/modules/reading-sessions/*, frontend/src/features/journal/LogSessionDialog.tsx |  | Fixed
1 | R1-08 | Book page and details | major | Modal buttons silently do nothing without a matching edition | Circe (no editions) > 'Start / Resume Reading Session'; Piranesi (physical only) > 'Open Digital Reader'. | Hidden, disabled, or explained. | Both silently go to the book page. | Modal buttons fell back to navigating to the book page. | Modal shows only working actions and explains/offers to add a copy otherwise. | frontend/src/features/library/BookQuickActionModal.tsx |  | Fixed
1 | R1-09 | Tracking journal statistics | minor | Statistics contradict themselves; language data messy | Statistics > Daily. | Consistent numbers. | Summary counts 1 session while the chart says 'No reading sessions in this period yet'; languages 'Unknown 6' and lowercase 'english 2'; 'Bunko' listed as an author. | The chart's empty state keyed on minutes, not sessions; language labels weren't normalised. | Chart distinguishes 'no sessions' from 'sessions under a minute'; languages shown as names. ('Bunko' as author was seed data; reading goals aren't in the SRS.) | frontend/src/features/statistics/ActivityChart.tsx, backend/src/modules/statistics/statistics.service.ts |  | Fixed
1 | R1-10 | Library adding finding books | minor | Catalogue search isn't typo-tolerant and is slow; no status on add | Add a book > 'tomorow and tomorrow and tomorrow'. | The right book near the top. | After 6-8s: unrelated results. Confusing language chips; manual form lacks page count/cover; always added as Want to Read. | Google Books answered first with poor relevance; the universe check could hijack results; no caching; original language defaulted to 'Japanese'. | Open Library title search merged in; results ranked by title match; universe check only for named universes; searches cached an hour; choose Want to read / Reading now / Already read when adding; calm metadata line replaces off-palette chips. (Catalogue-side typo tolerance depends on the providers.) | backend/src/modules/metadata/metadata.service.ts, frontend/src/features/library/AddBookDialog.tsx |  | Fixed
1 | R1-11 | Library adding finding books | minor | 'Remove from library' gave no visible response | Book page > 'Remove from library'. | A confirmation, then the book is gone. | Nothing visible; the book stayed. | Used the browser's native confirm(), which the tester never saw. | In-app confirmation dialog that says what's kept. | frontend/src/features/library/BookDetailPage.tsx |  | Fixed
1 | R1-12 | Shelves organizing | minor | Odd shelf grouping, per-row scrollbars, inverted toggle | Shelves > All Volumes; Covers/Spines toggle; mobile. | Books share shelves; the active view is clear. | One book per tall row under its own title; every row has a scrollbar; the active toggle option is the dim one; the choice doesn't stick; arrows cover art on mobile. | Rows per one-book series/genre; overflow-x-auto made rows scroll vertically; active toggle was the dark pill; arrows forced visible on mobile. | Rows need two books; overflow-y hidden with a thin themed scrollbar; light active pill with aria-pressed, remembered; arrows on focus/hover only. | frontend/src/features/shelves/* |  | Fixed
1 | R1-13 | Speed reliability | minor | Slow loads with little feedback | Library, Shelves, book pages; status dropdown. | Fast, with placeholders. | Covers blank for 3-5s on every visit; a big modal spinner; status change ~3s while the old value still shows. | Opening a book ran series discovery and a cover search synchronously (2-3s); covers had no placeholder; status change waited for the server. | Both moved to the background (book fetch ~72 ms); lazy covers on a paper tint; skeleton in the modal; optimistic status updates. | backend/src/modules/library/library.service.ts, frontend/src/features/library/BookCover.tsx, frontend/src/lib/api/works.ts |  | Fixed
1 | R1-14 | Notes highlights reviews | minor | Reviews and notes are basic | Rated, reviewed, added and edited a note. | Half stars, dated notes, spoiler/private options. | Whole stars only; notes undated with only a 'Book' tag; highlights impossible (R1-01). | Notes showed no date; ratings are whole stars by SRS §14. | Notes show their date (and position); the review box says reviews and notes are private. Half stars not added: SRS §14 sets whole 5-star ratings. | frontend/src/features/notes/NotesPanel.tsx, frontend/src/features/reviews/ReviewPanel.tsx |  | Partly fixed
1 | R1-15 | Assistant chat | polish | Odd reply after declining a follow-up | 'rate piranesi 5 stars' > asked to mark Finished > 'nah not yet'. | 'Okay, I'll leave it as Reading.' | 'Okay, I kept Piranesi.' (sounds like it nearly removed it). | The decline message was the generic 'Okay, I kept X.' | Follow-up offers can say what 'no' means (general core hook): 'Okay, Piranesi stays as Reading.' | backend/src/modules/assistant/domain/DomainPack.ts, backend/src/modules/assistant/AIRuntime.ts, backend/src/modules/assistant/domains/books/pipeline/replies.ts |  | Fixed
1 | R1-16 | First impression onboarding | polish | No forgot-password, no import of an existing history | Login and register pages; Settings. | Forgot password; Goodreads/StoryGraph import. | Neither exists. | Password reset needs email delivery (none configured); importing other platforms is SRS §37, which needs product approval. | Not built. A first-run welcome now explains the three ways to start (add, read/log, assistant). | frontend/src/features/library/LibraryPage.tsx |  | Won't fix (needs approval)
1 | R1-17 | Look and feel | polish | Sidebar scrolls away on long pages | Scrolled a long book page on desktop. | Navigation and Sign out stay in reach. | The sidebar scrolls with the content. | Sidebar wasn't sticky. | Sticky full-height sidebar on desktop. | frontend/src/components/layout/AppShell.tsx |  | Fixed
What the tester liked
The visual identity feels made for readers: warm paper, serif headings, a wooden bookcase with real-looking spines, and personal copy.
Inline shelf creation from a book page is excellent; shelf chips toggle with a clear checkmark.
Reviews and notes feel smooth: stars, Favourite and Want-to-reread toggles, an instant 'Saved.', and notes that edit in place.
The assistant's opt-in screen is honest about what data goes where; when it worked it understood 'tbr', read back notes, and undo worked.
Solid mobile layout: bottom tab bar, two-column cover grid, full-width search, and a cleanly stacked book page.

## Round 2
Round 2 | 2026-10-23 | Meera, book-lover persona (code-blind agent; browser only)
Local: frontend :5174, API :3100; assistant model not configured (no NVIDIA_API_KEY), tester told so. Fresh seeded account with an original 5-chapter EPUB.
Area | Score | Tester's reason
First impression onboarding | 8 | Calm login and a 3-step welcome for a new account; quick sign-up. No Goodreads/StoryGraph import.
Library adding finding books | 7 | Rich results and the status choice on add are lovely, but search took 10-15s, a one-letter typo found nothing, covers slow.
Book page and details | 6 | Clean, nice privacy line, but rating/favourite silently lost without 'Save review'; no progress, dates or highlights on the page.
Reading experience | 5 | Strong appearance panel, search, chapter jumps, resume; but no paragraph breaks, titles printed three times, highlights not drawn, no selection in 3D Flip, font change resets position, broken phone layout.
Tracking journal statistics | 6 | Excellent manual log; but reflection Save does nothing, raw 'epubcfi(...)' in the journal, inflated session time, a stale session blocks new ones, no finish dates.
Shelves organizing | 7 | Charming bookcase with genre rows, instant shelf creation; empty shelf can't add books, faint 'Covers' toggle, unlabeled tabs.
Notes highlights reviews | 5 | Good selection popover and margin notes; highlights not drawn, reader notes absent from the book page, no central notes view, no review confirmation.
Assistant chat | 6 | Exact commands and undo work, honest about the missing model, excellent privacy text; brittle with natural phrasing; 'dnf'd klara' added a different book.
Look and feel | 8 | Feels hand-crafted for book lovers; some developer text and low-contrast controls.
Speed reliability | 5 | Slow search and covers, logged out once on refresh, dead reflection save, stuck active session, shrunken reader after closing a session.
Overall | 6 | Has the soul of a reader's app; reading/highlighting and session tracking still have rough edges.
Issues and fixes
Round | ID | Area | Severity | Title | Steps | Expected | Actual | Root cause | Fix | Files | Commit | Status | Verified in round
2 | R2-01 | Notes highlights reviews | major | Highlights are saved but never drawn on the page text | Paginated mode, selected a passage, chose green; reopened the book. | The passage shows green highlighting. | Listed in the Highlights panel, but the text stays plain. | Highlights were stored with their text and chapter but the reflowed pages were plain strings; nothing located the saved text on a page. | Each page now keeps the character offsets of its text, saved highlights are found in the chapter (forgiving line breaks) and drawn in their colour, stronger on light paper. | frontend/src/features/reader/flow-layout.ts, frontend/src/features/reader/FlowReaderPage.tsx |  | Fixed
2 | R2-02 | Reading experience | major | Reflowed text has no paragraph breaks and repeats each chapter title | Opened the novella and turned pages. | Proper paragraphs; title once. | Each chapter is one block starting 'The Last Lantern The Last Lantern Aldmere had...' under a heading saying the same. | EPUB extraction stripped every tag and collapsed whitespace, so <title> + <h1> + paragraphs became one run ('The Last Lantern The Last Lantern Aldmere...'). | Body only, one paragraph per block element, entities decoded, a heading that repeats the chapter title dropped; chapter graph v4 re-indexes existing books. | backend/src/modules/reader/epub-indexer.ts, backend/src/modules/reader/chapter-graph.ts |  | Fixed
2 | R2-03 | Assistant chat | major | 'dnf'd klara' added a different book | 'dnf'd klara, the robot pov wasnt for me' with Klara and the Sun owned. | Mark Klara and the Sun DNF, or ask. | 'I've added Klāre by Otto Hinnerk to your library as Did Not Finish.' | 'klara' covered 1 of 4 title words (score 75 < 80), so it wasn't treated as the owned book and the auto-add searched the catalogue. | A title's opening words name it (score 88); a near match to an owned title never auto-adds a stranger's book, the tool asks instead. | backend/src/modules/assistant/domains/books/text/match.ts, backend/src/modules/assistant/domains/books/pipeline/planChecks.ts |  | Fixed
2 | R2-04 | Tracking journal statistics | major | Reflection 'Save' after a session does nothing | Reader X > typed a reflection > Save (x3). | Saves and closes. | Dialog stays open, no message; the reflection never reaches the Journal. | Save sent the end call again with a reflection; the server treated the already-ended session's new reflection as 'different data' (409) and the error was swallowed. | A reflection can follow the end (only when none exists); errors are shown; Save/Skip return to the book page. | backend/src/modules/reading-sessions/reading-sessions.service.ts, frontend/src/features/reader/FlowReaderPage.tsx, frontend/src/features/reader/ReflectionPrompt.tsx |  | Fixed
2 | R2-05 | Tracking journal statistics | major | A stale reader session blocks new sessions with a developer-style error | Left the reader by navigating away; later 'Start a reading session' on another book. | Start a timer, or offer to end the old one. | 'Another session is already active for this user' and nothing shows or ends it. | Leaving the reader without closing it left the session ACTIVE; the 409 text was developer wording with no way out. | Leaving the reader pauses its session; the clash names the book ('You're still in a reading session for ...') and offers 'Pause that one and start here'. | frontend/src/features/reader/FlowReaderPage.tsx, frontend/src/features/library/SessionConflict.tsx, backend/src/modules/reading-sessions/reading-sessions.service.ts |  | Fixed
2 | R2-06 | Tracking journal statistics | major | Session time includes time away from the reader | Left the reader open in the background, came back, closed it. | Only active reading time. | '6 min of reading' for about a minute. | Duration was end minus start, including time away. | Sessions record paused time (pausedAt, pausedSeconds); a hidden tab pauses and resumes; the idle sweep pauses from the last page turn; paused time is subtracted. | backend/prisma/schema.prisma, backend/src/modules/reading-sessions/*, frontend/src/features/reader/FlowReaderPage.tsx |  | Fixed
2 | R2-07 | Tracking journal statistics | major | Journal shows a raw internal position | Journal after a reader session. | 'Chapter 4, 67%'. | '6 min · EPUB · epubcfi(/6/2!/4/2/1:0) → ch4' | The journal printed stored positions (CFI, chapter ids) as-is. | Entries carry startLabel/endLabel: chapter titles (from the chapter graph, CFIs by spine step), 'p. N' for pages. | backend/src/modules/journal/journal.service.ts, frontend/src/features/journal/JournalPage.tsx |  | Fixed
2 | R2-08 | Reading experience | major | Can't select text in the default 3D Flip mode | Drag-select and double-click in 3D Flip. | Text selects; highlight popover appears. | Dragging starts a page curl; only works after switching to Paginated, with no hint. | react-pageflip took mouse and touch input in 3D Flip mode, so a drag curled the page instead of selecting. | The flipbook no longer takes pointer input: text selects in every mode; pages turn with the buttons, arrow keys or a swipe. | frontend/src/features/reader/FlowReaderPage.tsx |  | Fixed
2 | R2-09 | Reading experience | major | Phone reader shows ~6 lines in a tiny inset card | Mobile 375x812, reader. | Text fills the screen. | Small inner card, ~6 lines per page; bookmark and View Original missing from the toolbar. | Pages were always A4 halves of a two-page spread, tiny on a phone; ten toolbar icons overflowed. | Below 768px one page fills the screen; Note, Translate, Music, View Original and 'Not where you left off?' move into a More menu. | frontend/src/features/reader/FlowReaderPage.tsx, frontend/src/features/ai/TranslatePanel.tsx |  | Fixed
2 | R2-10 | Book page and details | major | Rating and Favourite silently lost without 'Save review' | Clicked 5 stars and Favourite, refreshed. | Saved instantly or warned. | All empty after refresh; no 'Saved' confirmation even when saving works. | Stars and Favourite only changed the form; nothing saved until 'Save review'. | Rating, favourite and reread save on click with a 'Saved.' note; unsaved review text is kept. | frontend/src/features/reviews/ReviewPanel.tsx |  | Fixed
2 | R2-11 | Speed reliability | major | Logged out on refresh mid-session | ~6 min after sign-in, refreshed the reader. | Stay signed in. | Sent to /login, then landed on Library. | Refresh tokens rotate on every use; two refreshes with the same cookie (StrictMode's double restore, parallel 401s, several tabs reloading) made the loser look like token reuse and signed the reader out. | One refresh at a time: shared within a tab and serialised across tabs with a Web Lock; a failed refresh never clears a newer token. | frontend/src/lib/api/client.ts, frontend/src/lib/auth-context.tsx |  | Fixed
2 | R2-12 | Reading experience | minor | Changing font size resets to the start | Page 2 of 8 > font +2. | Same passage. | 'Page 1 of 10', back at chapter 1. | Re-pagination re-anchored to the chapter's first page, and the flipbook wasn't remounted at the new index. | Position is chapter + character offset; after any re-layout the reader lands on the page holding that passage. | frontend/src/features/reader/FlowReaderPage.tsx, frontend/src/features/reader/flow-layout.ts |  | Fixed
2 | R2-13 | Reading experience | minor | 'View Original' loses your place and has no way back | At 67% > View Original. | Same position; toggle back. | Opens at chapter 1, 0%; no side padding, default Times; only Close. | The original view ignored the reading view's position (epub.js only finds an idref with '#') and had only Close. | Opens at the chapter you were on; 'Back to reading view' button. | frontend/src/features/reader/ReaderPage.tsx, frontend/src/features/reader/EpubReader.tsx |  | Fixed
2 | R2-14 | Reading experience | minor | Reader renders shrunken after closing a session | X > Session ended > Skip. | Back to the library, or a normal reader. | A small card mid-screen; X vs Skip inconsistent. | The reflection prompt replaced the reader, and Save/Skip went 'back' in history, sometimes into the reading view of the ended session. | The prompt sits over the book; both readers return to the book page afterwards. | frontend/src/features/reader/FlowReaderPage.tsx, frontend/src/features/reader/ReaderPage.tsx |  | Fixed
2 | R2-15 | Reading experience | minor | Pages half empty; first spread's left page blank | Read the first spreads on desktop. | Pages fill. | Text stops two-thirds down; next spread has one line then a new chapter. | Pagination estimated characters per page (deliberately conservative) and the first page was laid out as a lone 'cover'. | Pages are measured with the real fonts in an offscreen copy of the page (about 97% full, nothing clipped); the cover slot is used only for a real cover. | frontend/src/features/reader/flow-layout.ts, frontend/src/features/reader/FlowReaderPage.tsx |  | Fixed
2 | R2-16 | Reading experience | minor | 'mins left' estimate depends on layout | Changed font size, chapter list, mobile. | Stable estimate. | ~32, ~40, ~68, ~50 at the same spot. | 'mins left' was pages left x 4. | Progress and time left come from characters read (about 230 words a minute), the same at any font size. | frontend/src/features/reader/FlowReaderPage.tsx, frontend/src/features/reader/ReaderProgressScrubber.tsx |  | Fixed
2 | R2-17 | Reading experience | minor | Arrow keys don't turn pages | Right arrow in the reader. | Next page. | Nothing. | No keyboard handling in the reading view. | Left/Right arrows and Page Up/Down turn pages (not while typing or in a dialog). | frontend/src/features/reader/FlowReaderPage.tsx |  | Fixed
2 | R2-18 | Notes highlights reviews | minor | Reader highlights/notes absent from the book page; no central notes view | Highlight with a margin note > book page. | Listed on the book page. | 'Notes: No notes yet.' | The book page listed notes only; highlights lived in the reader. | 'Highlights & quotes' on the book page, newest first, with colour, margin note and a link back into the book. (A separate all-books notes page isn't built.) | frontend/src/features/notes/BookHighlights.tsx, frontend/src/features/library/BookDetailPage.tsx |  | Partly fixed
2 | R2-19 | Assistant chat | minor | Natural follow-ups and phrasing variants fail | 'finsihed circe, 4 stars and put it on comfort reads', 'put it on comfort reads', 'put circe on comfort reads', 'actually undo that'. | Handled, or each simple command. | The same canned 'not set up' reply each time; a message typed while pending wasn't sent on Enter. | 'put X on Y' needed the word 'shelf'; 'it' was bound to the previous turn's subject; 'actually undo that' wasn't recognised. | Shelves named without 'shelf' (and 'add X to Y' when Y is a shelf or X is theirs); 'it' is the book named in the same message; undo accepts fillers. The tester's sentence now does status, rating and shelf without a model. | backend/src/modules/assistant/domains/books/conversation/quickCommands.ts, backend/src/modules/assistant/domains/books/pipeline/preRoute.ts, backend/src/modules/assistant/domains/books/pipeline/undo.ts |  | Fixed
2 | R2-20 | Tracking journal statistics | minor | No finish dates, so 'this year' can't be answered | Marked books Finished; asked 'how many books did i read this year'. | Finish dates; yearly count. | 'Bunko can only tell which were this year from logged reading sessions...' | No completion date was stored. | UserWork.finishedAt (SRS §18.2), set when marked Finished, backfilled from the last session; shown on the book page; 'this year' uses it. | backend/prisma/schema.prisma, backend/src/modules/library/library.service.ts, backend/src/modules/assistant/domains/books/conversation/libraryAnswers.ts, frontend/src/features/library/BookDetailPage.tsx |  | Fixed
2 | R2-21 | Library adding finding books | minor | Book search slow and typo-intolerant | 'tomorow and tomorrow and tomorrow'. | Right book within a couple of seconds. | 10-15s spinner, unrelated results. | Catalogue providers are slow on a cold query and have no fuzzy matching; results are cached for an hour after the first search. | Not changed this round (needs a provider-side change). |  |  | Open
2 | R2-22 | Library adding finding books | minor | Status doesn't follow reading; no progress shown | Read to 67%, back to Library. | Status Reading; progress on the card. | Still Want to Read; no progress; 'Continue Reading' before ever opening. | Opening a book never changed its status; the button always said 'Continue Reading'. | Starting or logging a session moves Want to Read to Reading (never Finished/DNF); 'Start reading' until the first session. (Progress on cards not built.) | backend/src/modules/library/library.service.ts, backend/src/modules/reading-sessions/reading-sessions.service.ts, frontend/src/features/library/ContinueReadingButton.tsx |  | Partly fixed
2 | R2-23 | Tracking journal statistics | minor | Languages 'Unknown 6' and lowercase 'english'; EPUB reading added no pages | Statistics > Languages. | 'English'; EPUB pages counted. | 'Unknown 6 books', 'english 1 book'; pages read only from the manual log. | The page passed language names through Intl.DisplayNames, which reads 'english' as a valid code and returns it lowercased; books with no language said 'Unknown'. | Only codes are looked up, names are capitalised; missing language reads 'Not recorded'. (EPUB pages need a start position; unchanged.) | frontend/src/features/statistics/chart-format.ts, frontend/src/features/statistics/StatisticsPage.tsx |  | Partly fixed
2 | R2-24 | Shelves organizing | minor | An empty shelf offers no way to add books | New shelf '2026 faves'. | An 'Add books' picker. | Text only, no button. | No way to add books from a shelf. | 'Add books' on custom shelves and in the empty state: a searchable picker of library books. | frontend/src/features/shelves/AddToShelfDialog.tsx, frontend/src/features/shelves/ShelvesPage.tsx |  | Fixed
2 | R2-25 | Shelves organizing | polish | Low-contrast toggle and unlabeled shelf tabs | Shelves page. | Readable toggle; named tabs. | 'Covers' dark brown on near-black; tabs read as unnamed buttons; odd brown scrollbar strip. | Inactive toggle text at 70% opacity on near-black; dark wood scrollbar on the paper background. | Full-strength toggle text; shelf tabs say their name and count and report pressed state; light paper scrollbar. | frontend/src/features/shelves/ShelvesPage.tsx, frontend/src/index.css |  | Fixed
2 | R2-26 | Tracking journal statistics | polish | Journal order wrong; entries can't be edited | Logged a session after another the same day. | Newest first; edit/delete. | Newer entry below the older; clicking opens the book. | Journal sorted by start time, so a session logged after the fact sorted by when it began. | Sorted by when sessions ended. (Editing an entry isn't built.) | backend/src/modules/journal/journal.service.ts |  | Partly fixed
2 | R2-27 | Book page and details | polish | Duplicate status, marketing-blurb synopsis, small icon issues | Book pages and reader toolbar. | One status control, clean synopsis, labelled icons. | Pill plus dropdown; synopsis starts with press quotes; unlabeled icon; bookmark icon never fills. | Status showed as a pill and a dropdown; catalogue copy opens with press quotes; bookmark icon never reflected state. | One labelled status control; leading press quotes and ALL-CAPS banners trimmed for display; the bookmark fills when the chapter is bookmarked. | frontend/src/features/library/BookDetailPage.tsx, frontend/src/features/library/synopsis.ts, frontend/src/features/reader/FlowReaderPage.tsx |  | Fixed
2 | R2-28 | First impression onboarding | polish | No import or account basics for switchers | Welcome screen and Settings. | Import, yearly goal, export, change password. | None present. | Import (SRS §37), reading goals, export and password change aren't in the MVP scope. | Not built; needs product approval. |  |  | Won't fix (needs approval)
What the tester liked
Feels made by people who love books: the wooden bookcase with genre rows, the sepia reader with a warmth slider, serif headings, 'Session ended... Nice work.'
Plain, excellent privacy wording around AI (translation and the assistant).
Manual 'Log reading' is great: current read first, page-order validation, a clear confirmation.
Adding a book flows well: the status choice is part of adding, then 'Add a copy'.
The assistant does what it can reliably and reversibly, with a working undo.

## Round 3
Round 3 | 2026-10-23 | Meera, book-lover persona (code-blind agent; browser only)
Local: frontend :5174, API :3100; assistant model not configured (no NVIDIA_API_KEY). The seeded account's password reached the tester in a follow-up message, which its safety check refused to type, so it tested with a fresh account that had no EPUB: the reader was not tested this round.
Area | Score | Tester's reason
First impression onboarding | 7 | Quick, warm sign-up and a helpful 3-step welcome; no Goodreads/StoryGraph import and wrong metadata in the first search.
Library adding finding books | 5 | Own-library search and filters work; catalogue search ~5s and original language plainly wrong (Piranesi 'Written in Japanese').
Book page and details | 5 | Rating, favourite, shelves, notes, editions work; saved review blank after a refresh; description shows raw markdown.
Reading experience | not tested | Not tested: no readable EPUB on the tester's account.
Tracking journal statistics | 7 | Paper logging pleasant and validated, clean journal and stats; a timed session vanished on refresh, entries can't be edited or deleted, 'No genre: 5'.
Shelves organizing | 6 | Charming bookcase and add-books works; 'JAP' spine badge, nearly invisible Covers/Spines and Add books controls, no rename.
Notes highlights reviews | 5 | Notes persist; a review that disappears on reload (with Save enabled) breaks trust.
Assistant chat | 6 | Plain commands, undo, history all work; natural phrasing misread, odd alternatives, added an Indonesian edition of Circe.
Look and feel | 7 | Crafted for readers with good mobile nav; developer-ish copy and low-contrast controls.
Speed reliability | 6 | No errors or sign-outs; state that only appears after in-app navigation and 5-10s searches/replies.
Overall | 6 | Bones and taste are there; data vanishing on refresh and wrong metadata stop a recommendation.
Issues and fixes
Round | ID | Area | Severity | Title | Steps | Expected | Actual | Root cause | Fix | Files | Commit | Status | Verified in round
3 | R3-01 | Notes highlights reviews | major | Saved review is blank after a page refresh, and Save invites wiping it | Write a review, Save changes ('Saved.'), refresh the page. | Review text still there. | Box empty with Save enabled; in-app navigation shows it again. | Regression from R2-10: the panel moved its 'last saved text' marker before React ran the state update, so on a fresh load the update compared against the new text and kept the empty draft. | The previous value is captured before the marker moves; verified: text survives a refresh and Save stays disabled until edited. | frontend/src/features/reviews/ReviewPanel.tsx |  | Fixed
3 | R3-02 | Shelves organizing | major | Spine language badge reads 'JAP' | Shelves > Spines, a book marked Japanese. | A neutral code or no badge. | 'JAP' on the spine, an ethnic slur. | Spines printed the first three letters of the language name. | Two-letter ISO codes (JA, TA, ID); no badge when the language isn't known. | frontend/src/lib/language-code.ts, frontend/src/features/shelves/BookSpine.tsx |  | Fixed
3 | R3-03 | Library adding finding books | major | Original language wrong in search results and on the book | Add a book > search 'piranesi', 'Convenience Store Woman'. | Piranesi original English; Murata original Japanese. | Every Open Library result 'Orig: Japanese'; Google Books Murata 'Orig: English'; carried into Shelves and Statistics. | Book search filled in 'Japanese' as the original language whenever a catalogue didn't give one (Google's edition language was also used as the original). | Original language is left empty unless known; a migration clears the guessed value on existing books (where the edition isn't Japanese and the title has no Japanese script). | backend/src/modules/metadata/metadata.service.ts, backend/prisma/migrations/20261023090000_clear_guessed_original_language |  | Fixed
3 | R3-04 | Assistant chat | major | Assistant added a foreign-language edition of Circe | 'I just finished Circe by Madeline Miller, 4 stars'. | The English edition. | Indonesian description, 'IND' spine, Indonesian in Statistics. | Two editions with the same title and author were de-duplicated first-come, and the Indonesian one arrived first. | De-duplication and ranking prefer the reader's language for Latin-script queries (other scripts unaffected). | backend/src/modules/metadata/metadata.service.ts |  | Fixed
3 | R3-05 | Book page and details | minor | Description shows raw markdown | Piranesi's book page. | Formatted or plain text. | '**From the *New York Times* bestselling author...**' with asterisks. | Some catalogues send markdown emphasis. | Shown as plain text (bold/italic markers removed; arithmetic asterisks left alone). | frontend/src/features/library/synopsis.ts |  | Fixed
3 | R3-06 | Tracking journal statistics | minor | Active paper session disappears on refresh | Start a reading session, refresh. | Still in progress, with elapsed time. | 'Start a reading session' again; no timer while running. | The paper-session panel only remembered its session in page state. | GET /reading-sessions/open restores it after a refresh; the panel shows 'Reading for N min · started 4:05 PM'. | backend/src/modules/reading-sessions/*, frontend/src/lib/api/sessions.ts, frontend/src/features/library/PhysicalSessionPanel.tsx |  | Fixed
3 | R3-07 | Assistant chat | minor | Natural phrasing becomes part of the title | 'gave up on Klara and the Sun around halfway, it just wasn't for me'. | Klara and the Sun marked DNF. | 'I couldn't find a book called Klara and the Sun around halfway' with unrelated alternatives. | After the comma was cut, 'around halfway' stayed in the title. | How-far phrases (halfway, page 120, 40%...) are dropped, and when one of the reader's titles opens the phrase, that title is used. | backend/src/modules/assistant/domains/books/conversation/quickCommands.ts |  | Fixed
3 | R3-08 | Shelves organizing | minor | Shelf controls nearly invisible on dark wood | Shelves: Covers/Spines toggle and Add books. | Readable controls. | Dark text on dark brown. | The controls used wood-100, a colour step the palette doesn't define, so the class produced nothing; paper-600 and some moss steps (used in 36 files) were missing too. | Undefined shades replaced; paper-600, moss-200/400/800 added to the palette and DESIGN.md. | frontend/src/features/shelves/ShelvesPage.tsx, frontend/tailwind.config.js, DESIGN.md |  | Fixed
3 | R3-09 | Tracking journal statistics | minor | Journal entries can't be edited or deleted | Try to remove an accidental 1-minute session. | Edit or delete per entry. | Entries only link to the book. | No delete for sessions. | Delete (with confirmation) on each journal entry: DELETE /reading-sessions/:id, finished sessions only; highlights and notes from it stay. | backend/src/modules/reading-sessions/*, frontend/src/features/journal/JournalPage.tsx, frontend/src/lib/api/journal.ts |  | Partly fixed
3 | R3-10 | First impression onboarding | minor | No Goodreads/StoryGraph import | Settings and empty Library. | CSV import. | None. | Importing other platforms is SRS §37 (needs product approval). | Not built. |  |  | Won't fix (needs approval)
3 | R3-11 | Assistant chat | polish | Contradictory status confirmation | 'started The Left Hand of Darkness yesterday'. | 'Added as Reading.' | 'I've added ... as Want to Read. I've marked ... as Reading.' | The merged 'added as X' reply didn't match authors with initials ('Ursula K. Le Guin'). | The author part may contain periods; one sentence now. | backend/src/modules/assistant/domains/books/pipeline/replies.ts |  | Fixed
3 | R3-12 | Look and feel | polish | Developer-ish or inconsistent wording | Shelves, Add book, Settings. | Consistent reader language. | 'Catalog Racks & Collections:', 'All Volumes' vs 'All Books', 'To Read', 'Parts Count', 'Your Added Language', source badges, 'search vectors', consent named differently on two pages. | Labels written from the code's point of view. | 'Your shelves', 'All books', 'Want to Read', 'Parts'/'Chapters', 'Language you read it in', no source badges, 'a private search index', and the setting renamed 'Assistant and book summaries' to match the Assistant page. | frontend/src/features/shelves/ShelvesPage.tsx, frontend/src/features/library/AddBookDialog.tsx, frontend/src/features/ai/ai-disclosure.ts, frontend/src/features/ai/AiSettingsCard.tsx |  | Fixed
3 | R3-13 | Library adding finding books | polish | Manual add lacks status; adding a copy gives no feedback | Add custom book manually; Add a copy > Physical copy. | Status choice; confirmation. | Silently Want to Read; no feedback. | The manual form had no status choice; adding a copy closed silently. | 'Add it as' on the manual form too; 'Copy added. You can start reading it now.' (Page count isn't stored on a work.) | frontend/src/features/library/AddBookDialog.tsx, frontend/src/features/library/BookQuickActionModal.tsx |  | Partly fixed
3 | R3-14 | Tracking journal statistics | polish | Statistics filler | Statistics with no EPUBs and no genres. | Caveats only when relevant. | 'EPUB pages are estimated' with no EPUBs; a lone 'No genre: 5' bar. | Caveat always shown; an all-unknown breakdown drew one bar. | The EPUB caveat appears only with EPUB reading; 'None of your books has a genre recorded yet.' (Yearly goals and a ratings chart aren't in the SRS.) | frontend/src/features/statistics/StatisticsPage.tsx, frontend/src/features/statistics/BreakdownList.tsx |  | Partly fixed
3 | R3-15 | Book page and details | polish | Review buttons shown with only a rating | Rate a book with no review text. | 'Remove review' hidden until a review exists. | Both buttons present. | The review buttons showed whenever a review row existed, including rating-only. | They appear only once there is review text. | frontend/src/features/reviews/ReviewPanel.tsx |  | Fixed
What the tester liked
The paper-reading flow: friendly page-order check, 'Logged 30 min of Piranesi, pages 1-42', 'Session saved - 1 min. Nice reading.'
The Shelves bookcase: wooden racks, serif spines, drag and keyboard rearranging.
The Assistant's plain commands, a clear undo that says what it reversed, history that survives a refresh.
Warm, calm design that adapts well to a phone: bottom tab bar, no horizontal scroll.
Honest privacy copy ('Private: only you can see your ratings, reviews and notes, so spoil away.').
The first-run three-step welcome.

## Round 4
Round 4 | 2026-10-23 | Meera, book-lover persona (code-blind agent; browser only)
Local: frontend :5174, API :3100; assistant model not configured (no NVIDIA_API_KEY). Browser pane already signed in to the seeded account with the readable EPUB; desktop (800px pane) and phone 375x812.
Area | Score | Tester's reason
First impression onboarding | 7 | Warm and calm with clear empty states; onboarding not seen (already signed in); the Assistant asks to turn AI on before saying what it does.
Library adding finding books | 6 | Adding works and results look great; ~16s search, confusing labels, 'Already read' stamps today, no way to edit metadata.
Book page and details | 6 | Rating, favourite, review, shelves, status save nicely; finish date not editable, 'Bunko Sample Press' as author, 'Chapter · ch1' labels.
Reading experience | 5 | Lovely typography, 3D curl and phone layout; wrong current chapter (footer, bookmarks, notes), scroll and View Original lose your place, View Original's first chapter broken.
Tracking journal statistics | 8 | The journal is the best part; timer survived a refresh; paper logging easy.
Shelves organizing | 8 | Charming bookcase, multi-add works, shelf toggles on the book page; adding a bit slow.
Notes highlights reviews | 5 | Highlights show on page and book page and persist; deleting one deleted another with its note; chapter notes on the wrong chapter; tapping a highlight does nothing.
Assistant chat | 7 | Honest about the missing model; commands, undo and questions work; 'can you put klara on my comfort reads shelf' listed the shelf; 'last night' ignored.
Look and feel | 8 | Made for readers; a few developer-ish labels and cramped phone layouts.
Speed reliability | 6 | Never signed out, nothing lost; blank spinner on every load, slow search and shelf adds, View Original blanks each page turn.
Overall | 6 | Would track reading here today, but can't yet trust the reader with place and highlights.
Issues and fixes
Round | ID | Area | Severity | Title | Steps | Expected | Actual | Root cause | Fix | Files | Commit | Status | Verified in round
4 | R4-01 | Notes highlights reviews | major | Deleting one highlight also deleted another and its margin note | Reader > Highlights (3) > trash on the Quote, no feedback, click again. | Only the Quote deleted, with confirm or undo. | The Quote and the yellow highlight with its margin note both gone; no confirmation or feedback. | Deleting waited for the server before the list changed, so a second click landed on the next highlight as it slid up. | Highlights leave the list at once (restored if the delete fails), and deleting asks in place: Delete / Keep. | frontend/src/features/reader/AnnotationsDrawer.tsx, frontend/src/lib/api/annotations.ts |  | Fixed
4 | R4-02 | Reading experience | major | Current chapter wrong: footer, chapter list, bookmarks, notes | Turn pages with arrows in 3D Flip / scroll; bookmark in The Customs House; 'This chapter' note in A Ledger in Salt. | Everything names the chapter being read. | Footer lags 1-2 chapters; bookmark labelled and jumping to the wrong chapter; note saved as 'Chapter · ch1'. | The page-flip handler was memoised on the first render, before chapters loaded, so the chapter name never followed page turns; notes showed the stored chapter id. | The flip handler goes through a ref to the latest code; the chapter name is derived from the current chapter; notes carry positionLabel (the chapter title). | frontend/src/features/reader/FlowReaderPage.tsx, backend/src/modules/notes/notes.service.ts, backend/src/modules/reader/position-labels.ts |  | Fixed
4 | R4-03 | Reading experience | major | Scroll mode doesn't reopen where you left off | Scroll mode, go to The Customs House (~58%), refresh. | Reopens there. | Top of chapter 1 at 0% while the footer says another chapter. | Scroll mode tried to scroll before its chapters were on screen, and tracked position with requestAnimationFrame, which stalls in a background tab, so offsets stayed at 0. | Position is chapter + offset in scroll mode too, restored once the chapters render; tracking uses a timer. | frontend/src/features/reader/FlowReaderPage.tsx |  | Fixed
4 | R4-04 | Reading experience | major | View Original's first chapter broken; switching views loses place | At A Ledger in Salt, View Original, then Back to reading view. | Same spot, normal layout, place kept. | Huge heading, paragraphs in 4-5 narrow columns, opens at chapter 1, 0% / '20 min left'; back in reading view at 0%; ~2s blank page per turn; no highlights. | The original-file view treated the first section of any book as a cover (narrow columns); position loss came from R4-03; the time estimate was guessed from chapter counts. | Only a section marked as a cover is laid out as one; the place carries both ways; no time guess in the original view. (Page-turn blanking and highlights in the original view unchanged.) | frontend/src/features/reader/EpubReader.tsx, frontend/src/features/reader/ReaderPage.tsx |  | Partly fixed
4 | R4-05 | Book page and details | major | Finish date can't be set or changed | Finish a book; add as 'Already read'; 'finally finished circe last night, 4 stars'. | Editable date; 'last night' = yesterday. | Plain text; 'Already read' stamps today (inflating this year's count); Circe got today. | finishedAt could only be 'now'; 'Already read' dated today; the assistant ignored 'last night'. | Editable 'Finished on' date (PATCH /works finishedAt, no future dates); 'Already read' starts undated; 'finished X last night' dates it yesterday and says so. | backend/src/modules/library/*, frontend/src/features/library/BookDetailPage.tsx, frontend/src/features/library/AddBookDialog.tsx, backend/src/modules/assistant/domains/books/actions/libraryTools.ts, backend/src/modules/assistant/domains/books/conversation/quickCommands.ts |  | Fixed
4 | R4-06 | Reading experience | minor | Search result jumps to the chapter, not the match | Search 'ledger', click a result. | Scroll to and mark the match; search box focused. | Top of chapter, nothing marked; first typing lost. | Search results carried only the chapter; the box wasn't focused. | Jumps to the page with the match, marks the words for a few seconds; the box is focused. | frontend/src/features/reader/FlowReaderPage.tsx, frontend/src/features/reader/InBookSearchDrawer.tsx |  | Fixed
4 | R4-07 | Reading experience | minor | No end-of-book moment | Read to 100%. | Offer to mark finished / rate. | Nothing; '1 min left' at 100%; status stays Reading. | No handling of the last page. | 'The end. Finished <title>?' with Mark as finished; 'Last page' instead of '1 min left'. | frontend/src/features/reader/FlowReaderPage.tsx, frontend/src/features/reader/ReaderProgressScrubber.tsx |  | Fixed
4 | R4-08 | Library adding finding books | minor | Add-book search slow, labels confusing | Search 'The Housekeeper and the Professor'. | Fast results, clear labels. | ~16s; 'Added: English' badge on every result; leading 'The' dropped. | Coloured chips per result ('Added: English' meant the language you'd read it in). | One quiet line ('Originally Japanese · 14 chapters'), synopsis cleaned. (Catalogue speed unchanged.) | frontend/src/features/library/AddBookDialog.tsx |  | Partly fixed
4 | R4-09 | Library adding finding books | minor | Library search can't combine author and title; no metadata editing | Search 'ishiguro klara'; try to fix an author/cover. | Finds the book; an Edit option. | No match; no edit; inconsistent placeholder covers. | Library search matched the whole phrase against title or author. | Each word must match the title or an author. (Editing book details isn't built: works are shared catalogue entries.) | backend/src/modules/library/library.service.ts |  | Partly fixed
4 | R4-10 | Book page and details | minor | 'Open the book' on a highlight doesn't go to it | Book page > Highlights > Open the book. | Opens at that highlight. | Opens at the last position. | The link opened the book at the last position. | 'Read it in the book' opens the reader at that highlight. | frontend/src/features/notes/BookHighlights.tsx, frontend/src/features/reader/FlowReaderPage.tsx |  | Fixed
4 | R4-11 | Notes highlights reviews | minor | Highlights can't be edited from the page; weak feedback | Click a highlight; save one with a note or a Quote. | Edit/recolour/delete on click; confirmation. | Nothing on click; no confirmation; toolbar covers the selection; quotes cut off; raw colour names. | Highlights on the page weren't interactive; saving was silent. | Tapping a highlight opens your highlights; 'Highlight saved' / 'Quote saved' notice; colour labels replaced by a swatch. | frontend/src/features/reader/FlowReaderPage.tsx, frontend/src/features/reader/AnnotationsDrawer.tsx |  | Fixed
4 | R4-12 | Reading experience | minor | Dark theme leaves light surfaces | Appearance > Dark. | Whole reader dark. | Progress bar and Appearance panel stay cream; stray horizontal scrollbar. | The progress bar used fixed cream colours. | It takes the reading theme's colours. (The Appearance panel stays light.) | frontend/src/features/reader/ReaderProgressScrubber.tsx |  | Partly fixed
4 | R4-13 | Reading experience | minor | Menus don't close with Escape or an outside click | Open the bookmarks dropdown or the phone '...' menu. | Closes. | Stays open; two menus open at once. | No Escape or outside-click handling. | Escape closes menus and panels; clicking outside closes the dropdowns. | frontend/src/features/reader/FlowReaderPage.tsx |  | Fixed
4 | R4-14 | Tracking journal statistics | minor | Tiny accidental sessions; inconsistent page fields | Open and close a book within a minute; compare Log reading and ending a timed session. | Very short visits not logged; same page fields. | 'Under a minute' sessions counted; free-text vs numeric page fields. | Every opened reader session was kept. | Closing a book within a minute leaves no journal entry. (The paper-session form still asks for a chapter or page as text, which SRS §12.9 requires.) | frontend/src/features/reader/FlowReaderPage.tsx |  | Partly fixed
4 | R4-15 | Assistant chat | minor | Natural shelf request answered with a list | 'can you put klara on my comfort reads shelf'. | Adds it or asks. | Listed the shelf; 'something like piranesi' ignored. | 'can you ...' read as a question, so it was answered from the library. | Polite requests ('can you put ...?') are commands. | backend/src/modules/assistant/domains/books/pipeline/preRoute.ts |  | Fixed
4 | R4-16 | Look and feel | polish | Developer-ish text and cramped phone layouts | Desktop and phone. | Reader wording, tidy phone layouts. | 'CHAPTERS / TOC', 'Chapter · ch1', 'Drag, or use the keyboard' on phone, small chapter titles, cramped Editions header and Journal dates, full-screen Appearance sheet. | Leftover technical labels; fixed heading size; dates squeezing journal entries on phones. | 'Chapters', plainer shelves subtitle, chapter titles a step above body text, journal dates above the title on phones. | frontend/src/features/reader/ReaderPage.tsx, frontend/src/features/shelves/ShelvesPage.tsx, frontend/src/features/reader/FlowReaderPage.tsx, frontend/src/features/journal/JournalPage.tsx |  | Partly fixed
4 | R4-17 | Speed reliability | polish | Blank spinner on every full page load | Refresh any page. | App shell immediately. | 1-2s blank page; typing lost; 'Maximum update depth exceeded' and some 404s in the console. | The app waits for the session to be restored before drawing anything. | Not changed this round. |  |  | Open
What the tester liked
Beautiful reading surface: serif type, spacing, sepia/paper themes, a satisfying 3D curl; font changes and refresh keep your place in Flip mode.
The Journal: reflection, highlights, margin notes and chapter notes grouped per session; an honest delete dialog.
The 'Session ended' reflection ritual, and a paper session that survives a refresh.
The Shelves bookcase with spine/cover toggle and multi-select 'Add books'.
An honest Assistant with accurate commands, undo and library answers, and clear AI privacy text.
A good phone layout: clean icon toolbar, well-sized reading column.

## Round 5
Round 5 | 2026-10-28 | Meera, book-lover persona (code-blind agent; browser only)
Local: frontend :5174, API :3100 with AI_PROVIDER=nvidia and a real NVIDIA_API_KEY (live model calls, no mock). Seeded fresh account (qa.round5.1793127205@bunko.test) with AI consent pre-granted, a small library, two shelves, and one readable EPUB.
Area | Score | Tester's reason
First impression onboarding | 8 | Clean, calm, book-themed login; already signed in to the seeded account so full onboarding wasn't seen, but nothing felt generic.
Library adding finding books | 7 | Adding by title/author with real metadata/cover enrichment works well, but the library grid shows a generic placeholder tile even when the book's detail page has a real cover.
Book page and details | 8 | Rich, well-organized page (description, series, shelves, rating, review, notes, highlights); rating and notes persisted reliably on retest.
Reading experience | 9 | Genuinely delightful EPUB reader: 3D-flip and scroll modes, 4 legible themes, font/line/margin controls, in-book search, working highlights, bookmarks, and a thoughtful end-of-book flow.
Tracking journal statistics | 6 | Logging/viewing/deleting sessions works with a nice delete confirmation, but a logged date was off by one day and a typed session reflection was silently discarded.
Shelves organizing | 6 | The physical bookshelf visualization is the best-looking part of the app, but the Shelves page's own 'Add books to shelf' dialog does nothing when you click Add book.
Notes highlights reviews | 7 | Highlighting with the color picker, the Highlights sidebar, and reviews/ratings/notes all saved and persisted, but the lost session reflection and some first-attempt save fragility hold it back.
Assistant chat | 7 | Accurate and grounded on in-scope library questions with a working undo and clear loading states, but off-topic questions reliably time out even on retry, and 'i started reading circe' fails to parse despite Circe being the book just recommended.
Look and feel | 9 | Serif typography, warm paper palette, the physical bookshelf, thoughtful copy, and a transparent AI-data-use settings page -- feels made by book people, not a generic template.
Speed reliability | 6 | Most interactions are fast, but real reproducible bugs surfaced: the broken shelf add-books dialog, a lost session reflection, an off-by-one journal date, one unexplained mid-session logout, and tooltips that get stuck open and block clicks underneath.
Overall | 7 | A charming, well-designed reading app with one of the best in-browser EPUB readers tested, let down by a handful of real functional bugs a careful reader would hit within a single normal session.
Issues and fixes
Round | ID | Area | Severity | Title | Steps | Expected | Actual | Root cause | Fix | Files | Commit | Status | Verified in round
5 | R5-01 | Shelves organizing | blocker | "Add book" button in the Shelves page's "Add books to [shelf]" dialog does not work | Shelves > created a new shelf 'rainy day reads' via '+ New Shelf' > clicked 'Add books' on the empty shelf > checked Circe and Piranesi > clicked 'Add book' (repeated with ref clicks, coordinate clicks, and Enter while focused). | Selected books get added to the shelf and the dialog closes/updates the count. | Nothing happens -- dialog stays open, shelf still shows '0 books'. Workaround: toggling the shelf tag on each book's own detail page works correctly. |  |  |  |  | Open
5 | R5-02 | Tracking journal statistics | major | Reflection typed into the reader's "Session ended" dialog is never saved | Finished 'The Lantern Keeper of Aldmere' in the reader > 'Close the book' > 'Session ended / 6 min of reading. Nice work.' dialog > typed a reflection > Save. | The reflection text appears in the Journal entry, the book's Notes, or its Review. | The reflection text is gone entirely. The Journal entry shows an unrelated earlier highlight instead; Notes/Review stay empty even after reload. |  |  |  |  | Open
5 | R5-03 | Tracking journal statistics | minor | Logged reading session date is off by one day | Journal > 'Log reading' > book Piranesi, Day field showed '28-10-2026' (today), Minutes 45, From page 10, To page 55, reflection text, 'Log reading'. | Journal entry shows 'Oct 28, 2026' matching the selected date. | Entry is listed under 'Oct 27, 2026' -- one day earlier, suggesting a timezone conversion bug. |  |  |  |  | Open
5 | R5-04 | Assistant chat | major | Off-topic assistant questions reliably time out (even on retry) | In Assistant chat, after several successful book-related exchanges, sent 'whats the weather like today'. Waited 30s -> timeout message. Clicked 'Try again', waited another 30s. | Either a quick graceful redirect, or at least a successful retry. | Both the original attempt and the retry timed out after ~30s each with the same message. A normal on-topic question sent right after answered correctly within ~10s, so the failure seems specific to off-topic prompts. |  |  |  |  | Open
5 | R5-05 | Assistant chat | minor | Natural phrasing "i started reading circe" fails to resolve the book despite Circe being in the library and just discussed | After being recommended 'Circe by Madeline Miller' in the previous message, typed 'i started reading circe'. | The assistant recognizes 'circe' as the book just discussed and marks it Reading. | "I couldn't find a book called 'reading circe'..." -- it matched the whole phrase as a title instead of parsing 'started reading' as the verb phrase. Retyping with the full title worked. |  |  |  |  | Open
5 | R5-06 | Speed reliability | major | Unexpected full session logout with no warning, not reproduced on retry | On a book detail page (The Name of the Wind), clicked 'Add note', typed a note, clicked the '+ Add note' trigger button. | Note dialog opens or note saves; if a session genuinely expired, a clear message should explain why. | The app silently navigated to /login with all session state lost, no toast or explanation. Logging back in and repeating the exact steps worked fine every subsequent time. |  |  |  |  | Open
5 | R5-07 | Look and feel | minor | Toolbar tooltip/panel overlays get stuck open and block clicks underneath | In the reader, clicked the Translate icon (shows 'isn't set up on this server yet' tooltip), then clicked other toolbar icons or chapter-list entries without first dismissing the Translate tooltip. | Clicking elsewhere should dismiss the previous tooltip automatically, or at least not intercept the click. | The tooltip stays on top, intercepting clicks meant for elements beneath it. Escape or its own close button dismisses it, but a casual user wouldn't know to do that and would think the buttons are broken. |  |  |  |  | Open
5 | R5-08 | Library adding finding books | minor | Library grid cover art falls back to a generic placeholder even when real cover art exists | Added 'The Name of the Wind' via the Assistant, then viewed the Library grid. | Since the book's detail page and quick-view popup both show real cover art, the grid thumbnail should match. | The Library grid shows a generic orange 'T' placeholder tile, while every other metadata field is correctly enriched. |  |  |  |  | Open
5 | R5-09 | Tracking journal statistics | polish | Settings page AI-features copy contradicts actual working behavior | Settings > 'AI features' section. | Messaging consistent with the Assistant chat being clearly live and working with a real AI model. | Footer text reads "AI features aren't set up on this server yet -- your choice is saved for when they are", which is stale and could confuse a user about whether their data is actually being sent anywhere. |  |  |  |  | Open
What the tester liked
The 3D-flip/scroll EPUB reader is excellent: real pagination with chapter titles, 4 legible reading themes, font/line-spacing/margin controls, in-book search that jumps to the exact page, and highlights that persist across reload.
The physical bookshelf visualization on the Shelves page (wood shelf texture, genre grouping, Covers/Spines toggle, drag to rearrange) is delightful and unlike any generic tracker UI.
The Assistant correctly grounds its answers in the user's actual library (accurate counts, correct want-to-read list, sensible recommendations) and has a working, reliable undo for its last action.
The 'Session ended' flow after finishing a book (reading-time summary, 'Finished [Book]?' prompt, auto-set finish date) mirrors how a real reader thinks about wrapping up a book.
Settings' AI-features section is unusually transparent about exactly what data is sent to which third-party service and when -- genuinely trust-building rather than generic boilerplate.